## BOQ
CONTRACT SANRAL N.002-300-2022/2R | [5 empty] | Estimate @ 26/05/2025
ITEM |  |  |  | DESCRIPTION | UNIT | SCHEDULED QTY | FINAL EST. QTY | PREVIOUS QTY | CURRENT QTY | TO DATE QTY | RATE R | SCHEDULED AMOUNT | FINAL EST. AMOUNT | VARIANCE | COMMENTS | [5 empty] | TEN Civils Rate | TEN Civils Amount
C1.2 |  |  |  | GENERAL REQUIREMENTS AND PROVISIONS
C1.2.1 |  |  |  | ENVIRONMENTAL MANAGEMENT
| C1.2.1.1 |  |  | Monitoring of compliance with and reporting on the EMP | month | 12 | 9 | 0 | 0 | 0 | 35000 | 420000 | 315000 | 105000 | Original Contract Duration | #VALUE!
| C1.2.1.2 |  |  | Dedicated environmental officer (if specified in the Contract Documentation) | month | 12 | 9 | 0 | 0 | 0 | 24000 | 288000 | 216000 | 72000 | Original Contract Duration | #VALUE!
0
C1.2.2 |  |  |  | Programming and Reporting | [11 empty] | 0
| C1.2.2.3 |  |  | Reviewing and updating a Scheme 2 Initial Programme | lump sum | 1 | 1 | 0 | 1 | 1 | 10000 | 10000 | 10000 | 0 |  | -10000
| C1.2.2.4 |  |  | Reviewing and updating a Scheme 2 Full Programme | lump sum | 1 | 1 | 0 | 1 | 1 | 10000 | 10000 | 10000 | 0 |  | -10000
| C1.2.2.5 |  |  | Reviewing and updating a Scheme 2 programme every month | month | 12 | 9 | 0 | 0 | 0 | 3500 | 42000 | 31500 | 10500 | Original Contract Duration | #VALUE!
| C1.2.2.6 |  |  | Preparation and submission of all information and reports specified in the Contract Documentation | month | 12 | 9 | 0 | 0 | 0 | 5800 | 69600 | 52200 | 17400 | Original Contract Duration | #VALUE!
0
C1.2.3 |  |  |  | Routine road maintenance of existing public roads within the Site of Works or other public roads outside the Site of the Works which are used as detours
| C1.2.3.7 |  |  | Base and/or surface patching using hot plant mixed asphalt | ton (t) | 500 | 0 | 0 | 0 | 0 | 1500 | 750000 | 0 | 750000 | Contractor likely wont do this item | #VALUE!
| C1.2.3.8 |  |  | Replacement of damaged guardrails including posts | metre (m) | 15200 | 0 | 0 | 0 | 0 | 1090 | 16568000 | 0 | 16568000 | Nil, masured below | #VALUE!
| C1.2.3.13 |  |  | Liaison with the routine road maintenance contractor | month | 12 | 9 | 0 | 0 | 0 | 5000 | 60000 | 45000 | 15000 | Original Contract Duration | #VALUE!
0
C1.2.4 |  |  |  | Stakeholder Liaison | month | 12 | 9 | 0 | 6 | 6 | 10000 | 120000 | 90000 | 30000 | original Contract Duration | #VALUE!
0
C1.2.5 |  |  |  | SAFETY
| C1.2.5.1 |  |  | Health and Safety Plan | lump sum | 1 | 1 | 0 | 1 | 1 | 18000 | 18000 | 18000 | 0 |  | -18000
| C1.2.5.2 |  |  | Implementation of health and safety plan | month | 12 | 9 | 0 | 2 | 2 | 5000 | 60000 | 45000 | 15000 | original Contract Duration | #VALUE!
0
PC1.2.7 |  |  |  | Road Safety Audits
| C1.2.7.1 |  |  | Stage 4 work zone traffic management audit | provisional sum | 1 | 0.21667 |  | 0 |  | 150000 | 150000 | 32500 | 117500 | Actual | #VALUE!
| C1.2.7.2 |  |  | Handling cost, profit and all other charges in respect of item C1.2.7.1 | percentage (%) | 150000 | 3250 |  | 0 |  | 10% | 15000 | 325 | 14675 |  | -15000
| C1.2.7.3 |  |  | Stage 5 pre-opening stage traffic safety audit | provisional sum | 1 | 0.20507 |  | 0 |  | 150000 | 150000 | 30760 | 119240 | Actual | #VALUE!
| C1.2.7.4 |  |  | Handling cost, profit and all other charges in respect of item C1.2.7.3 | percentage (%) | 150000 | 3076 |  | 0 |  | 10% | 15000 | 307.6 | 14692.4 |  | -15000
0
C1.2.8 |  |  |  | DAYWORKS
| C1.2.8.1 |  |  | Personnel
|  | (a) |  | Unskilled labourer | hour (h) | 100 | 0 |  | 0 |  | 50.03 | 5003 | 0 | 5003 | Estimated to be Nil | #VALUE!
|  | (b) |  | Semi-skilled labourer | hour (h) | 100 | 0 |  | 0 |  | 67.33 | 6733 | 0 | 6733 | Estimated to be Nil | #VALUE!
|  | (c) |  | Skilled labourer | hour (h) | 100 | 0 |  | 0 |  | 93.6 | 9360 | 0 | 9360 | Estimated to be Nil | #VALUE!
|  | (d) |  | Gang leader | hour (h) | 100 | 0 |  | 0 |  | 93.5 | 9350 | 0 | 9350 | Estimated to be Nil | #VALUE!
|  | (e) |  | Foreman | hour (h) | 100 | 0 |  | 0 |  | 135 | 13500 | 0 | 13500 | Estimated to be Nil | #VALUE!
|  | (f) |  | Skilled artisan | hour (h) | 100 | 0 |  | 0 |  | 125 | 12500 | 0 | 12500 | Estimated to be Nil | #VALUE!
0
C1.2.8.2 |  |  |  | Construction Equipment
|  | (b) |  | (b)Vibratory roller (self-propelled, 9 - 12 ton mass) | hour (h) | 24 | 0 |  | 0 |  | 450 | 10800 | 0 | 10800 | Estimated to be Nil | #VALUE!
|  | (c) |  | (c)Pneumatic roller (9 - 12 ton mass) | hour (h) | 24 | 0 |  | 0 |  | 450 | 10800 | 0 | 10800 | Estimated to be Nil | #VALUE!
|  | (f) |  | Excavator (14.7 tonnes) | h | [10 empty] | #VALUE!
|  | (g) |  | Compressor (including hammers, tools, etc. capacity 0.02m³/s @ 620kPa) | h | [10 empty] | #VALUE!
0
C1.2.8.3 |  |  |  | Vehicles
|  | (a) |  | (a)Light delivery vehicle (minimum load capacity 1 ton) | kilometre (km) | 500 | 0 |  | 0 |  | 15 | 7500 | 0 | 7500 | Estimated to be Nil | #VALUE!
|  | (b) |  | (b)Flatbed truck (crane included, minimum load capacity 10 ton) | kilometre (km) | 500 | 0 |  | 0 |  | 35 | 17500 | 0 | 17500 | Estimated to be Nil | #VALUE!
|  | (c) |  | (c)Dump truck (load capacity approx 10 m3) | kilometre (km) | 500 | 0 |  | 0 |  | 35 | 17500 | 0 | 17500 | Estimated to be Nil | #VALUE!
0
C1.2.8.4 |  |  |  | Materials
|  | (a) |  | Procurement of materials | provisional sum | 1 | 0 |  | 0 |  | 100000 | 100000 | 0 | 100000 | Estimated to be Nil | #VALUE!
|  | (b) |  | Contractor's handling costs, profit and all other charges in respect of item C1.2.8.4(a) | percentage (%) | 100000 | 0 |  | 0 |  | 10% | 10000 | 0 | 10000 | Estimated to be Nil | #VALUE!
0
0
PC1.2.10 |  |  |  | Dispute Adjudication Board (DAB)
| C1.2.10.1 |  |  | Employer’s contribution to DAB (50%) | prime cost (PC) Sum | 1 | 0 |  | 0 |  | 400000 | 400000 | 0 | 400000 | Estimated to be Nil | #VALUE!
TOTAL CARRIED FORWARD TO SUMMARY | [11 empty] | 19376146 | 896592.6 | 18479553.4
C1.3 |  |  |  | THE CONTRACTOR'S SITE ESTABLISHMENT AND GENERAL OBLIGATIONS
PC1.3.1 |  |  |  | THE CONTRACTOR'S GENERAL OBLIGATIONS
| C1.3.1.1 |  |  | Fixed obligations | Lump Sum | 1 | 1 | 0 | 0.5 | 0.5 | 8629347.5 | 8629347.5 | 8629347.5 | 0 | [6 empty] | 1850878.5 | 1850878.5
| C1.3.1.2 |  |  | Value-related obligations | Lump Sum | 1 | 1 | 0 | 0 |  | 2132655 | 2132655 | 2132655 | 0
| C1.3.1.3 |  |  | Time-related obligations
|  | (a) |  | Mobilisation period | month | 3 | 3 | 0 | 3 | 3 | 489536 | 1468608 | 1468608 | 0 | Original Contract Duration
|  | (b) |  | Execution of the works | month | 9 | 9 | 0 | 3 | 3 | 745896 | 6713064 | 6713064 | 0 | Original Contract Duration | [5 empty] | 395000 | 2765000 | TEN Civils = 7mnths
| C1.3.1.4 |  |  | Suspension Cost
|  | (a) |  | De-establishment | number | 3 | 0 | 0 | 0 |  | 550000 | 1650000 | 0 | 1650000 | Assumed to be N/A
|  | (b) |  | Re-establishment | number | 3 | 0 | 0 | 0 |  | 550000 | 1650000 | 0 | 1650000 | Assumed to be N/A
|  | (c) |  | Suspension period | month | 3 | 0 | 0 | 0 |  | 150000 | 450000 | 0 | 450000 | Assumed to be N/A
|  | (d) |  | Engineer's cost | prime cost (PC) Sum | 1 | 0 | 0 | 0 |  | 1500000 | 1500000 | 0 | 1500000 | Assumed to be N/A
0
C1.3.2 |  |  |  | Contract Signboards | square metre (m²) | 20 | 19.2 | 0 | 0 |  | 1800 | 36000 | 34560 | 1440 | Actual
TOTAL CARRIED FORWARD TO SUMMARY | [11 empty] | 24229674.5 | 18978234.5 | 5251440 |  | 5251440 | [5 empty] | 4615878.5
C1.4 |  |  |  | FACILITIES FOR THE ENGINEER
C1.4.1 |  |  |  | SITE ACCOMMODATION
| C1.4.1.1 |  |  | Offices and conference room | square metre (m²) | 150 | 117 | 0 | 117 | 117 | 3840 | 576000 | 449280 | 126720 | Actual
| C1.4.1.2 |  |  | Laboratories | square metre (m²) | 200 | 101 | 0 | 101 | 101 | 1500 | 300000 | 151500 | 148500 | Actual
| C1.4.1.3 |  |  | Open concrete working floors and verandas | square metre (m²) | 100 | 132 | 0 | 132 | 132 | 600 | 60000 | 79200 | -19200 | Actual
| C1.4.1.4 |  |  | Roofs over open concrete working floors and verandas | square metre (m²) | 300 | 166.16 | 0 | 166.16 | 166.16 | 500 | 150000 | 83080 | 66920 | Actual
| C1.4.1.5 |  |  | Store rooms inside the laboratory | square metre (m²) | 20 | 15 |  | 15 | 15 | 800 | 16000 | 12000 | 4000 | Actual
| C1.4.1.6 |  |  | Car ports | number (No.) | 6 | 6 | 0 | 6 | 6 | 3500 | 21000 | 21000 | 0 | Actual
| C1.4.1.7 |  |  | Ablution unit (equipped as specified) |  |  | 0 |  | 0
|  | (a) |  | Smaller unit | number (No.) | 2 | 2 | 0 | 2 | 2 | 18000 | 36000 | 36000 | 0 | Actual
|  | (b) |  | Larger unit | number (No.) | 2 | 2 | 0 | 2 | 2 | 22000 | 44000 | 44000 | 0 | Actual
| C1.4.1.9 |  |  | Kitchen unit (equipped as per A1.4.7.1(g))) | number (No.) | 2 | 2 | 0 | 2 | 2 | 25000 | 50000 | 50000 | 0 | Actual
0
C1.4.2 |  |  |  | ITEMS MEASURED BY AREA |  |  |  |  | 0
| C1.4.2.1 |  |  | Shelving as specified, complete with brackets | square metre (m²) | 15 | 0 |  | 0 |  | 600 | 9000 | 0 | 9000 | Actual
| C1.4.2.2 |  |  | Work benches with a concrete slab top | square metre (m²) | 20 | 0 |  | 0 |  | 600 | 12000 | 0 | 12000 | Actual
| C1.4.2.3 |  |  | Work-benches with a wooden top | square metre (m²) | 10 | 0 |  | 0 |  | 600 | 6000 | 0 | 6000 | Actual
| C1.4.2.6 |  |  | Roller blinds, opaque type | square metre (m²) | 40 | 0 |  | 0 |  | 550 | 22000 | 0 | 22000 | Actual
| C1.4.2.7 |  |  | Venetian blinds | square metre (m²) | 40 | 21.12 | 0 | 21.12 | 21.12 | 550 | 22000 | 11616 | 10384 | Actual
| C1.4.2.8 |  |  | Notice boards | square metre (m²) | 24 | 10.92 |  | 10.92 | 10.92 | 1200 | 28800 | 13104 | 15696 | Actual
| C1.4.2.9 |  |  | White boards | square metre (m²) | 24 | 10.92 |  | 10.92 | 10.92 | 1200 | 28800 | 13104 | 15696 | Actual
[7 empty] | 0 |  | 0
C1.4.3 |  |  |  | ITEMS MEASURED BY NUMBER |  |  |  |  | 0
| C1.4.3.1 |  |  | Office swivel chair | number (No.) | 6 | 6 | 0 | 6 | 6 | 2500 | 15000 | 15000 | 0 | Actual
| C1.4.3.2 |  |  | Office chair | number (No.) | 20 | 20 | 0 | 20 | 20 | 800 | 16000 | 16000 | 0 | Actual
| C1.4.3.5 |  |  | Office desk with 3 drawers (at least one lockable drawer) | number (No.) | 5 | 5 | 0 | 5 | 5 | 4500 | 22500 | 22500 | 0 | Actual
| C1.4.3.6 |  |  | Typist desk (L-shaped) | number (No.) | 1 | 0 |  | 0 |  | 6000 | 6000 | 0 | 6000 | Actual
| C1.4.3.8 |  |  | Conference table | number (No.) | 1 | 1 | 0 | 1 | 1 | 27000 | 27000 | 27000 | 0 | Actual |  |  |  |  | #REF!
| C1.4.3.9 |  |  | Bookcase | number (No.) | 2 | 0 |  | 0 |  | 2200 | 4400 | 0 | 4400 | Actual
| C1.4.3.11 |  |  | General purpose steel cabinet with shelves | number (No.) | 6 | 4 | 0 | 4 | 4 | 2500 | 15000 | 10000 | 5000 | Actual
| C1.4.3.13 |  |  | 220/250 volt power outlet plug point | number (No.) | 20 | 14 | 0 | 14 | 14 | 650 | 13000 | 9100 | 3900 | Actual
| C1.4.3.14 |  |  | 400/231 volt 3-phase power outlet plug point | number (No.) | 2 | 0 |  | 0 |  | 650 | 1300 | 0 | 1300 | Actual
| C1.4.3.15 |  |  | Single 1500 mm, 58 watt fluorescent tube ceiling light | number (No.) | 10 | 14 | 0 | 14 | 14 | 900 | 9000 | 12600 | -3600 | Actual
| C1.4.3.18 |  |  | 7 watt LED bulb ceiling light | number (No.) | 10 | 0 |  | 0 |  | 650 | 6500 | 0 | 6500 | Actual
| C1.4.3.19 |  |  | Wash-hand basin | number (No.) | 2 | 2 | 0 | 2 | 2 | 950 | 1900 | 1900 | 0 | Actual
| C1.4.3.21 |  |  | Extractor fan | number (No.) | 5 | 0 |  | 0 |  | 800 | 4000 | 0 | 4000 | Actual
| C1.4.3.23 |  |  | Fire extinguisher 9,0 kg, dry powder type | number (No.) | 3 | 3 | 0 | 3 | 3 | 850 | 2550 | 2550 | 0 | Actual
| C1.4.3.24 |  |  | Air-conditioning unit | number (No.) | 7 | 7 | 0 | 7 | 7 | 19000 | 133000 | 133000 | 0 | Actual
| C1.4.3.27 |  |  | Waste paper basket | number (No.) | 6 | 0 |  | 0 |  | 100 | 600 | 0 | 600 | Actual
| C1.4.3.28 |  |  | UPS / Voltage stabiliser | number (No.) | 2 | 0 |  | 0 |  | 20000 | 40000 | 0 | 40000 | Actual
| C1.4.3.29 |  |  | A3 / A4 colour printer, copier, scanner | number (No.) | 1 | 1 |  | 1 |  | 12000 | 12000 | 12000 | 0 | Actual
| C1.4.3.31 |  |  | Rain gauge | number (No.) | 1 | 1 | 0 | 1 | 1 | 800 | 800 | 800 | 0 | Actual
| C1.4.3.33 |  |  | Digital thermometer | number (No.) | 2 | 0 |  | 0 |  | 300 | 600 | 0 | 600 | Actual
| C1.4.3.34 |  |  | Mobile outdoor weather station | number (No.) | 1 | 1 |  | 1 | 1 | 18000 | 18000 | 18000 | 0 | Actual
| C1.4.3.36 |  |  | Measuring wheel | number (No.) | 2 | 2 | 0 | 2 | 2 | 2000 | 4000 | 4000 | 0 | Actual
| C1.4.3.37 |  |  | First aid kit | number (No.) | 3 | 3 |  | 3 | 3 | 1200 | 3600 | 3600 | 0 | Actual
| C1.4.3.38 |  |  | Standpipe complete with 30m of 19mm dia. heavy duty hose pipe | number (No.) | 1 | 1 | 0 | 1 | 1 | 2500 | 2500 | 2500 | 0 | Actual
C1.4.4 |  |  |  | PRIME COST ITEMS
| C1.4.4.5 |  |  | The provision of internet connectivity and WiFi data for Engineer’s site staff | prime cost (PC) Sum | 1 |  |  | 0 |  | 12000 | 12000 | 0 | 12000 | 3 quotations not provided by Contractor
| C1.4.4.6 |  |  | Handling costs and profit in respect of item C1.4.4.5 | percentage (%) | 12000 |  |  | 0 |  | 10% | 1200 | 0 | 1200 | 3 quotations not provided by Contractor
| C1.4.4.11 |  |  | The provision of a complete 440/231 volt three phase electrical power installation, including all poles, insulators, wiring, switchboards, mains connections, meters etc. | prime cost (PC) Sum | 1 | 0.9983 |  | 0 |  | 150000 | 150000 | 149745.29 | 254.71 | Actual
| C1.4.4.12 |  |  | Handling costs and profit in respect of item C1.4.4.11 | percentage (%) | 150000 | 14974.529 |  | 0 |  | 10% | 15000 | 1497.4529 | 13502.5471 | Actual
| C1.4.4.15 |  |  | The provision of all gas installations required at the site offices, laboratories and at the Engineer’s staff accommodation (if required), including gas storage cylinders, tubing, regulators, gas burners and shut-off cocks | prime cost (PC) Sum | 1 |  |  | 0 |  | 100000 | 100000 | 0 | 100000 | Not required
| C1.4.4.16 |  |  | Handling costs and profit in respect of item C1.4.4.15 | percentage (%) | 100000 |  |  | 0 |  | 10% | 10000 | 0 | 10000 | Not required
C1.4.5 |  |  |  | SERVICES AT SITE OFFICES, LABORATORIES AND SITE ACCOMMODATION
| C1.4.5.1 |  |  | Fixed costs | lump sum | 1 | 1 | 0 | 1 | 1 | 18000 | 18000 | 18000 | 0 | Actual
| C1.4.5.2 |  |  | Running costs | month | 12 | 9 | 0 | 3 | 3 | 8000 | 96000 | 72000 | 24000 | Actual
C1.4.7 |  |  |  | SITE INSPECTION TRANSPORT
| C1.4.7.1 |  |  | Provision of a bus, mini-bus or combi van for site inspection purposes (10 seater with air conditioning) | per day | 24 | 12 |  | 0 |  | 2250 | 54000 | 27000 | 27000 | 6 months x 2
| C1.4.7.2 |  |  | Travel on site | kilometre (km) | 720 | 720 |  | 0 |  | 15 | 10800 | 10800 | 0 | 12 x 60km
C1.4.8 |  |  |  | SITE SECURITY MEASURES FOR THE ENGINEER'S FACILITIES
| C1.4.8.1 |  |  | Supply and installation of all required security measures at the Engineer’s site offices and laboratories | lump sum | 1 | 1 | 0 | 1 | 1 | 10000 | 10000 | 10000 | 0 | Actual
| C1.4.8.2 |  |  | Provision of security guards / watchmen and an armed response service at the Engineer’s site offices and laboratories | month | 12 | 9 | 0 | 3 | 3 | 54500 | 654000 | 490500 | 163500 | Actual
TOTAL CARRIED FORWARD TO SUMMARY | [11 empty] | 2871850 | 2033976.7429 | 837873.2571 |  | 837873.2571
C1.5 |  |  |  | ACCOMMODATION OF TRAFFIC
C1.5.1 |  |  |  | ACCOMMODATION OF PEDESTRIAN AND NON-MOTORISED TRAFFIC
| C1.5.1.1 |  |  | Accommodation of pedestrian and non-motorised traffic | month
C1.5.2 |  |  |  | Accommodation of vehicular traffic | month | 9 | 9 |  | 0 |  | 25000 | 225000 | 225000 | 0 | Actual
C1.5.3 |  |  |  | Liaison with traffic authorities | month | 9 | 9 | 0 | 3 | 3 | 5500 | 49500 | 49500 | 0 | Actual
PC1.5.7 |  |  |  | Temporary traffic control facilities
| C1.5.7.1 |  |  | Delineators including mounting bases and ballast:
|  | (a) |  | Single sided, reversible left or right
|  |  | (i) | Size 250 mm x 800mm | number (No) | 200 | 0 | 0 | 0 | 0 | 250 | 50000 | 0 | 50000
|  | (b) |  | Double sided, reversible left or right
|  |  | (i) | Size 250 mm x 800mm | number (No) | 2000 | 1000 | 0 | 0 | 0 | 180 | 360000 | 180000 | 180000 | 3 clousures
| C1.5.7.2 |  |  | Traffic cones, minimum height 750mm | number (No) | 100 | 100 | 0 | 0 | 0 | 325 | 32500 | 32500 | 0 | Provisional as per Tender
| C1.5.7.3 |  |  | Flagmen | man-shift | 4300 | 6510 | 0 | 0 | 0 | 540 | 2322000 | 3515400 | -1193400 | 3 closures over 5months
| C1.5.7.4 |  |  | Traffic controllers | man-shift | 500 | 0 | 0 | 0 | 0 | 350 | 175000 | 0 | 175000
| C1.5.7.5 |  |  | Provision of illuminated traffic signs
|  | (a) |  | Sign mounted amber flashing lights (2 lights with the specified power supply) mounted on a backing board which is:
|  |  | (ii) | 1200mm wide x 200mm high | Number (No) | 10 | 6 | 0 | 0 | 0 | 6500 | 65000 | 39000 | 26000
|  | (b) |  | Flashing LED illuminated arrow board | Number (No) | 10 | 6 | 0 | 0 | 0 | 4500 | 45000 | 27000 | 18000
|  | (c) |  | Illuminated road sign – R & TR series (900 size) | Number (No) | 120 | 102 | 0 | 0 | 0 | 1634 | 196080 | 166668 | 29412
|  | (d) |  | Illuminated road sign – TW series (1200 size) | Number (No) | 80 | 0 | 0 | 0 | 0 | 1765.2 | 141216 | 0 | 141216
|  | (g) |  | Illuminated road sign – TW series (1 200 mm size) | Number (No) | 150 | 0 | 0 | 0 | 0 | 580 | 87000 | 0 | 87000 | Duplicated
| C1.5.7.6 |  |  | Maintenance of illuminated traffic signs:
|  | (a) |  | Sign mounted flashing amber lights (a pair of two lights mounted on a separate backing board) | month | 9 | 9 | 0 | 0 | 0 | 500 | 4500 | 4500 | 0
|  | (b) |  | Flashing LED illuminated arrow board | month | 9 | 9 | 0 | 0 | 0 | 500 | 4500 | 4500 | 0
|  | (c) |  | Illuminated road sign – R & TR series (900 size) | month | 9 | 9 | 0 | 0 | 0 | 500 | 4500 | 4500 | 0
|  | (d) |  | Illuminated road sign – TW series (1200 size) | month | 9 | 9 | 0 | 0 | 0 | 500 | 4500 | 4500 | 0
|  | (g) |  | Illuminated road sign – TG/TIN series | month | 9 | 9 | 0 | 0 | 0 | 500 | 4500 | 4500 | 0
| PC1.5.7.10 |  |  | Moveable traffic signs |  |  | 0
|  | (a) |  | Regulatory signs. Temporary |  |  | 0
|  |  | (i) | R & TR series (900 diameter) | number | 10 | 102 | 0 | 0 | 0 | 150 | 1500 | 15300 | -13800
|  | (b) |  | Warning signs, temporary
|  |  | (ii) | TW series (1 200 mm size) | number | 10 | 33 | 0 | 0 | 0 | 150 | 1500 | 4950 | -3450
|  | (c) |  | Portable STOP and GO-RY signs | number | 4 | 0 | 0 | 0 | 0 | 150 | 600 | 0 | 600
|  | (d) |  | Road signs, STW-, DTG-, TGS- AND TG-series (excluding delineators and barricades) | number | 8 | 30 | 0 | 0 | 0 | 150 | 1200 | 4500 | -3300
|  | (e) |  | Moveable barricade/road sign combination (8m wide chevron and road closed types) | number | 2 | 0 | 0 | 0 | 0 | 150 | 300 | 0 | 300
|  | (f) |  | TIN 11-3 (600m) | number | 5 | 0 | 0 | 0 | 0 | 150 | 750 | 0 | 750
|  | (g) |  | TIN 11-3 (400m) | number | 5 | 54 | 0 | 0 | 0 | 150 | 750 | 8100 | -7350
|  | (h) |  | TIN 11-3 (200m) | number | 5 | 0 | 0 | 0 | 0 | 150 | 750 | 0 | 750
|  | (i) |  | TIN 11-4 (End/Thank you) | number | 5 | 0 | 0 | 0 | 0 | 150 | 750 | 0 | 750
C1.5.8 |  |  |  | Traffic safety officer | man-month | 18 | 15 | 0 | 0 | 0 | 90000 | 1620000 | 1350000 | 270000 | 9 months + 6 months night shift
C1.5.9 |  |  |  | Traffic safety vehicle | month | 18 | 15 | 0 | 0 | 0 | 120000 | 2160000 | 1800000 | 360000 | 9 months + 6 months night shift
C1.5.11 |  |  |  | Provision of safety equipment for visitors | [7 empty] | 0 | 0
|  | C1.5.11.1 |  | Reflective safety vests for visitors | number (No) | 10 | 10 | 0 | 0 | 0 | 50 | 500 | 500 | 0 | Provided
|  | C1.5.11.2 |  | Hard hats for visitors | No | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 0
C1.5.12 |  |  |  | Additional traffic accommodation facilities ordered by the Engineer: |  |  | 0
| C1.5.12.1 |  |  | Provision of additional traffic accommodation facilities | provisional sum | 1 | 0 | 0 | 0 | 0 | 100000 | 100000 | 0 | 100000 | Will be covered by the Contractor
| C1.5.12.2 |  |  | Handling cost, profit and all other charges in respect of item C1.5.12.1 | percentage (%) | 0 | 0 | 0 | 0 | 0 | 10% | 0 | 0 | 0
TOTAL CARRIED FORWARD TO SUMMARY | [11 empty] | 7659396 | 7440918 | 0 |  | 0 | [5 empty] | 218478
C1.6 |  |  |  | CLEARING AND GRUBBING
C1.6.1 |  |  |  | CLEARING
| C1.6.1.1 |  |  | Clearing with machines and some hard labour where necessary | hectare (ha) | 4.5 | 4.46 | 0 | 0 | 0 | 16500 | 74250 | 73590 | 660
C1.6.2 |  |  |  | GRUBBING
| C1.6.2.1 |  |  | Grubbing with machines and some hard labour where necessary | hectare (ha) | 4.5 | 4.46 | 0 | 0 | 0 | 18000 | 81000 | 80280 | 720
C1.6/C1.7.2 |  |  |  | HAULING
C1.6/C1.7.2.1 |  |  |  | Hauling material to spoil and off-loading it at a designated spoil or stockpile area:
|  | (a) |  | Cleared and grubbed material (organic matter and all other unsuitable or waste material) | cubic metre - kilometre (m³.km) | 450000 | 111500 | 0 | 0 | 0 | 7 | 3150000 | 780500 | 2369500
TOTAL CARRIED FORWARD TO SUMMARY | [11 empty] | 3305250 | 934370 | 2370880 |  | 2370880
C3.1 |  |  |  | DRAINS
C3.1.1 |  |  |  | Excavation for open drain
|  | (a) |  | 0m - 1.5m | cubic metre (m³) | 990 | 0 | 0 | 0 | 0 | 105 | 103950 | 0 | 103950
| C3.1.2.1 |  |  | Clearing, shaping and disposal of accumulated sediment in existing unlined open drains
| C3.1.2.1 |  |  | Using conventional methods | cubic metre (m³) | 1930 | 0 | 0 | 0 | 0 | 105 | 202650 | 0
C3.1.3 |  |  |  | Excavation, clearing and disposal of accumulated sediment in existing lined drains and drainage systems
| C3.1.3.1 |  |  | Using conventional methods (up to 1,5m):
|  | (a) |  | Manholes and inlet and outlet structures | cubic metre (m³) | 200 | 43.2 | 0 | 0 | 0 | 190 | 38000 | 8208 | 29792
|  | (b) |  | Culvert barrels | cubic metre (m³) | 540 | 540 | 0 | 0 | 0 | 190 | 102600 | 102600 | 0
|  | (c) |  | (c)Concrete or other lined side drains | cubic metre (m³) | 1930 | 1672.5 | 0 | 0 | 0 | 190 | 366700 | 317775 | 48925
C3.1.4 |  |  |  | Excavation and disposal of material for subsoil drainage systems:
| C3.1.4.1 |  |  | Excavating in all materials situated within the following depth ranges below the surface:
|  | (a) |  | 0m to 1.5m | cubic metre (m³) | 2460 | 911.4 | 0 | 0 | 0 | 190 | 467400 | 173166 | 294234
C3.1.5 |  |  |  | Impermeable backfilling to subsoil drainage system
| C3.1.5.1 |  |  | Unstabilised natural gravel obtained from approved source on the site | cubic metre (m³) | 1720 | 0 | 0 | 0 | 0 | 75 | 129000 | 0 | 129000
C3.1.7 |  |  |  | Natural permeable material in subsoil drainage systems
| C3.1.7.2 |  |  | Crushed stone obtained from commercial sources | cubic metre (m³) | 500 | 260.4 | 0 | 0 | 0 | 650 | 325000 | 169260 | 155740
C3.1.8 |  |  |  | Natural permeable material in subsoil drainage systems (approved natural sand):
| C3.1.8.2 |  |  | Natural sand from commercial sources | cubic metre (m³) | 250 | 651 | 0 | 0 | 0 | 650 | 162500 | 423150 | -260650
C3.1.9 |  |  |  | Pipes in subsoil drainage systems:
| C3.1.9.1 |  |  | U-PVC pipes and fittings, normal duty, complete with couplings | metre (m) | 6132.5 | 2170 | 0 | 0 | 0 | 65 | 398612.5 | 141050 | 257562.5
C3.1.11 |  |  |  | Geotextiles (A1)
| C3.1.11.1 |  |  | 0.15mm thick | square metre (m²) | 8590 | 4057.9 | 0 | 0 | 0 | 35 | 300650 | 142026.5 | 158623.5
C3.1.13 |  |  |  | Concrete outlet structures, manhole boxes, junction boxes and cleaning eyes for subsoil drainage systems
| C3.1.13.4 |  |  | Cleaning eyes | number (No.) | 60 | 4 | 0 | 0 | 0 | 1450 | 87000 | 5800 | 81200
C3.1.14 |  |  |  | Caps for subsoil drain pipes
| C3.1.14.3 |  |  | Other (PVC) | number (No.) | 60 | 8 | 0 | 0 | 0 | 185 | 11100 | 1480 | 9620
C3.1.15 |  |  |  | Repairing or replacing existing drainage systems | provisional sum | 1 | 1 | 0 | 0 | 0 | 100000 | 100000 | 100000 | 0
C3.1.22 |  |  |  | Test flushing of subsoil drain pipe system | number (No.) | 60 | 4 | 0 | 0 | 0 | 350 | 21000 | 1400 | 19600
C3.1/C1.7.2.2 |  |  |  | Hauling material to spoil and off-loading it at a designated spoil or stockpile area:
|  | (a) |  | Cleared and grubbed material (organic matter and all other unsuitable or waste material) | cubic metre - kilometre (m³.km) | 92000 | 56392.5 | 0 | 0 | 0 | 7 | 644000 | 394747.5 | 249252.5
TOTAL CARRIED FORWARD TO SUMMARY | [11 empty] | 3460162.5 | 1980663 | 1276849.5 |  | 1276849.5
C3.3 |  |  |  | CONCRETE KERBING AND CHANNELING, ASPHALT BERMS, CHUTES, DOWNPIPES, AS WELL AS CONCRETE, STONE PITCHED AND GABION LININGS FOR OPEN DRAINS
C3.3.8 |  |  |  | Linings for open drains:
| C3.3.8.1 |  |  | Cast in situ concrete lining (Class 20/19 for open drains) as per drawing contained in Appendix 15 | square metre (m²) | 280 | 279.93 | 0 | 0 | 0 | 2100 | 588000 | 587853 | 147
| C3.3.8.2 |  |  | ClassU2 surface finish to cast in situ concrete (Open Drains) | square metre (m²) | 8370 | 2235.1 | 0 | 0 | 0 | 140 | 1171800 | 312914 | 858886
C3.3.9 |  |  |  | Formwork to cast in situ concrete lining for open drains (Class F2 surface finish):
| C3.3.9.1 |  |  | To sides with formwork on the internal face only | square metre (m²) | 1000 | 542.5 | 0 | 0 | 0 | 430 | 430000 | 233275 | 196725
| C3.3.9.3 |  |  | To ends of slabs | square metre (m²) | 200 | 93.1292 | 0 | 0 | 0 | 430 | 86000 | 40045.5417 | 45954.4583
C3.3.10 |  |  |  | Sealed joints in concrete and stone pitched linings of open drains ((Polysulphide sealant) at 12m centres - Appendix 15) | metre (m) | 770 | 187.2883 | 0 | 0 | 0 | 65 | 50050 | 12173.7417 | 37876.2583
C3.3.12 |  |  |  | Reinforcement:
| C3.3.12.3 |  |  | Welded steel fabric (REF 193) | kilogram (kg) | 17760 | 4313.743 | 0 | 0 | 0 | 75 | 1332000 | 323530.725 | 1008469.275
TOTAL CARRIED FORWARD TO SUMMARY | [11 empty] | 3657850 | 1509792.0083 | 2148057.9917
C4.3 |  |  |  | EXISTING ROAD MATERIALS
C4.3.2 |  |  |  | Cleaning the existing road surface
| C4.3.2.1 |  |  | Cost to clean the road surface | provisional sum | 1 | 0 | 0 | 0 | 0 | 1000000 | 1000000 | 0 | 1000000
| C4.3.2.2 |  |  | Handling costs and profit in respect of item C4.3.2.1 | percentage (%) | 1000000 | 0 | 0 | 0 | 0 | 10% | 100000 | 0 | 100000
TOTAL CARRIED FORWARD TO SUMMARY | [11 empty] | 1100000 | 0 | 1100000 |  | 1100000
C8.5 |  |  |  | STANDARD CRACK SEALING
C8.5.1 |  |  |  | Standard crack sealing
| C8.5.1.1 |  |  | Cleaning cracks
|  | (b) |  | Cleaning crack with hot compressed air | metre (m) | 1100 | 0 | 0 | 0 | 0 | 65 | 71500 | 0 | 71500 | As per Kangela
| C8.5.1.2 |  |  | Applying herbicides for sealing cracks | litre (ℓ) | 180 | 0 | 0 | 0 | 0 | 21 | 3780 | 0 | 3780 | As per Kangela
| C8.5.1.3 |  |  | Priming | litre (ℓ) | 130 | 0 | 0 | 0 | 0 | 21 | 2730 | 0 | 2730 | As per Kangela
| C8.5.1.4 |  |  | Sealing the cracks
|  | (a) |  | Sealing using (CE-1) | litre (ℓ) | 330 | 0 | 0 | 0 | 0 | 21 | 6930 | 0 | 6930 | As per Kangela
TOTAL CARRIED FORWARD TO SUMMARY | [11 empty] | 84940 | 0 | 84940 |  | 84940
C8.8 |  |  |  | PATCHING AND EDGE BREAK REPAIR
C8.8.1 |  |  |  | Saw cutting pavement layers for patching
| C8.8.1.1 |  |  | Asphalt or bituminous surfacing to an average depth
|  | (a) |  | Not exceeding 50mm | metre (m) | 7000 | 0 | 0 | 0 | 0 | 56 | 392000 | 0 | 392000 | [6 empty] | 50 | 0
| C8.8.1.3 |  |  | Granular layers to an average depth
|  | (b) |  | Not exceeding 200mm | metre (m) | 7000 | 10041.8 | 0 | 0 | 0 | 56 | 392000 | 562340.8 | -170340.8 | [6 empty] | 75 | 753135
C8.8.2 |  |  |  | Excavation in existing pavements for patching (non-milling)
| C8.8.2.3 |  |  | Crushed Stone layers
|  | (b) |  | Not exceeding 10 m² including for edge repairs wider than 250mm | cubic metre (m³) | 1090 | 66.8 | 0 | 0 | 0 | 340 | 370600 | 22712 | 347888 | 834931.2 | [5 empty] | 450 | 30060
|  | (c) |  | Not exceeding 50 m² up to 100m² including for edge repairs wider than 250mm | cubic metre (m³) | 90 | 362 | 0 | 0 | 0 | 340 | 30600 | 123080 | -92480 | -221952 | [5 empty] | 311 | 112582
|  | (d) |  | Exceeding 100m² | cubic metre (m³) | 1090 | 456.79 | 0 | 0 | 0 | 340 | 370600 | 155308.6 | 215291.4 | 516699.36 | [5 empty] | 233 | 106432.07
| C8.8.2.4 |  |  | Asphalt layers
|  | (b) |  | Not exceeding 10 m² including for edge repairs wider than 250mm | cubic metre (m³) | 200 | 0 | 0 | 0 | 0 | 340 | 68000 | 0 | 68000 | 163200 | [5 empty] | 466.69 | 0
|  | (c) |  | Not exceeding 50 m² up to 100m² including for edge repairs wider than 250mm | cubic metre (m³) | 20 | 0 | 0 | 0 | 0 | 340 | 6800 | 0 | 6800 | 16320 | [5 empty] | 538.49 | 0
|  | (d) |  | Exceeding 100m² | cubic metre (m³) | 200 | 0 | 0 | 0 | 0 | 340 | 68000 | 0 | 68000 | 163200 | [5 empty] | 233.35 | 0
C8.8.3 |  |  |  | Compacting the floor of excavations for patching (Compacted to 95% MDD) | square metre (m2) | 12000 | 11812.31 | 0 | 0 | 0 | 45 | 540000 | 531553.95 | 8446.05 | 1114.8786 | [5 empty] | 4.98 | 58825.3038
C8.8.4 |  |  |  | Backfilling of excavations for patching with:
| C8.8.4.3 |  |  | Asphalt for a patch with a surface area (sand skelatal (congtinuosly graded) utilising a PG58E-22 binder utilisinga maximum binder replacement of 15%, compacted to 97% -% design voids of MVD
|  | (b) |  | Not exceeding 10 m² including for edge repairs wider than 250mm | ton (t) | 2900 | 167 | 0 | 0 | 0 | 1000 | 2900000 | 167000 | 2733000 | 1138750 | [5 empty] | 2402.45 | 401209.15
|  | (c) |  | Not exceeding 50 m² up to 100m² including for edge repairs wider than 250mm | ton (t) | 230 | 905 | 0 | 0 | 0 | 1000 | 230000 | 905000 | -675000 | -281250 | [5 empty] | 2456.29 | 2222942.45
|  | (d) |  | Exceeding 100m² | ton (t) | 2900 | 1141.97 | 0 | 0 | 0 | 1000 | 2900000 | 1141970 | 1758030 | 732512.5 | [5 empty] | 2247.32 | 2566372.0204
TOTAL CARRIED FORWARD TO SUMMARY | [11 empty] | 8268600 | 3608965.35 | 4659634.65 |  | 4659634.65 | [5 empty] | 6251557.9942
C8.9 |  |  |  | REPAIR OF SURFACE DEFECTS
C8.9.5 |  |  |  | Water Cutting
| C8.9.5.1 |  |  | Establishing of water cutting equipment on site | lump sum | 1 | 1 | 0 | 0 | 0 | 100000 | 100000 | 100000 | 0
| C8.9.5.2 |  |  | Applying herbicides for sealing cracks | square metre (m²) | 30000 | 34950 | 0 | 0 | 0 | 38 | 1140000 | 1328100 | -188100 | [6 empty] | 29.67 | 1036966.5
C8.9.6 |  |  |  | Trail sections for water cutting | square metre (m²) | 150 | 150 | 0 | 0 | 0 | 350 | 52500 | 52500 | 0
TOTAL CARRIED FORWARD TO SUMMARY | [11 empty] | 1292500 | 1480600 | -188100 | [7 empty] | 1036966.5
C9.1 |  |  |  | ASPHALT LAYERS
C9.1.1 |  |  |  | Asphalt mix designs
| C9.1.1.2 |  |  | Sand skeletal mix:
|  | (a) |  | Continuously graded base or surfacing (PG58E-22,Level II mix design) | lump sum | 1 | 1 |  | 0 |  | 150000 | 150000 | 150000 | 0 | [6 empty] | 220000 | 220000
C9.1.2 |  |  |  | Construction of trial sections
| C9.1.2.1 |  |  | Asphalt layers (sand skeletal (continuosly graded) utilising an PG58E-22 binder with a maximum binder replacement of 15%, 50mm, paver placed) | square metre (m²) | 1600 | 1920 |  | 0 |  | 212 | 339200 | 407040 | -67840 | [6 empty] | 345.17 | 662726.4
C9.1.3 |  |  |  | Application of bond coat
| C9.1.3.1 |  |  | Stable–grade 30% net bitumen emulsion as specified. Applied with a calibrated distributer | litre (ℓ) | 172000 | 161671.66 |  | 0 |  | 13 | 2236000 | 2101731.58 | 134268.42 | Excludes off-ramps | [5 empty] | 13.84 | 2237535.7744
| C9.3.1.3 |  |  | Applied by hand using brushes on all exposed transverse and longitudinal construction joints | litre (ℓ) | 800 | 376.57 |  | 0 |  | 21 | 16800 | 7907.97 | 8892.03 | [6 empty] | 8 | 3012.56
C9.1.5 |  |  |  | Asphalt surfacing
| C9.1.5.2 |  |  | Rehabilitation
|  | (e ) |  | Sand skeletal mix – continuously graded as defined (50mm, PG58E-22 utilising a maximum binder replacement of 15%, Level II mix design, paver placed) | ton (t) | 39000 | 40441.38 |  | 0 |  | 2565 | 53820000 | 103732139.7 | -49912139.7 | [6 empty] | 2293.5 | 92752305.03 | 10979834.67
C9.1.9 |  |  |  | Application of Rolled in chips
| C9.1.9.1 |  |  | By means of a chip spreader | square metre (m²) | 311540 | 0 |  | 0 |  | 15 | 4673100 | 0 | 4673100
C9.1.10 |  |  |  | Variation rates
| C9.1.10.1 |  |  | Bitumen (PG58E-22) | ton (t) |  | 0 |  |  |  | 3000 |  | Rate only | [7 empty] | 21054
| C9.1.10.2 |  |  | Aggregate | ton (t) |  | 0 |  |  |  | 3000 |  | Rate only | [7 empty] | 385
| C9.1.10.3 |  |  | Active filler (lime unless stated in Contract Document) | ton (t) |  | 0 |  |  |  | 3500 |  | Rate only | [7 empty] | 2434
C9.1.13 |  |  |  | Coring of asphalt layers
| C9.1.13.1 |  |  | 100mm diameter | number (No.) | 1730 | 0 |  | 0 |  | 300 | 519000 | 0 | 519000 | Being done by Roadlab | [5 empty] | 250 | 0 | No coring of asphalt?
C9.1.14 |  |  |  | Surface regularity testing as described in Clause A9.1.8.4 |  |  | 0
| C9.1.14.1 |  |  | Establishment of equipment: Inertial laser Profilometer | number (No.) | 1 | 1 |  | 0 |  | 35000 | 35000 | 35000 | 0 | [6 empty] | 75000 | 75000
| C9.1.14.2 |  |  | Profiler Surveys utilising equipment as specified - Base layers and surfacing layers | lane kilometre (km) | 80 | 89.2 |  | 0 |  | 3500 | 280000 | 312200 | -32200 | [6 empty] | 1320 | 117744
TOTAL CARRIED FORWARD TO SUMMARY | [11 empty] | 62069100 | 106746019.25 | -44676919.25 |  | -44676919.25 | [5 empty] | 96068323.7644
C11.4 |  |  |  | ROAD RESTRAINT SYSTEMS
C11.4.1 |  |  |  | Erecting of guardrails at 3.81m spacing
| C11.4.1.1 |  |  | Complete galvanised system compliant to SANS 1350: on timber posts
|  | (a) |  | on timber posts | metre (m) | 6140 | 8800 |  | 0 |  | 1000 | 6140000 | 8800000 | -2660000
| C11.4.1.2 |  |  | Terminal sections for 3.81m guardrails comprising of: |  |  | 0
|  | (a) |  | End Wings to SANS 1350 | number (No.) | 50 | 0 |  | 0 |  | 800 | 40000 | 0 | 40000
C11.4.6 |  |  |  | Reflective plates |  |  | 0
| C11.4.6.1 |  |  | Steel Plates | number (No.) | 3070 | 1157.8947 |  | 0 |  | 15 | 46050 | 17368.4211 | 28681.5789
C11.4.7 |  |  |  | Removing Existing Guardrails | metre (m) | 6140 | 8800 |  | 0 |  | 380 | 2333200 | 3344000 | -1010800
C11.4.14 |  |  |  | Nailing of gang nail plates on top of timber guardrail posts | number (No.) | 1620 | 2315.7895 |  | 0 |  | 55 | 89100 | 127368.4211 | -38268.4211
C11.4.15 |  |  |  | Disposal of existing guardrails |  |  | 0
| C11.4.15.1 |  |  | Straight or curved long guardrails | metre (m) | 6140 | 8800 |  | 0 |  | 60 | 368400 | 528000 | -159600
| C11.4.15.2 |  |  | End treatments with single guardrails | metre (m) | 620 | 0 |  | 0 |  | 80 | 49600 | 0 | 49600
TOTAL CARRIED FORWARD TO SUMMARY | [11 empty] | 9066350 | 12816736.8421 | -3750386.8421 |  | -3750386.8421
C11.6 |  |  |  | ROAD SIGNS
C11.6.1 |  |  |  | Road signboards with painted or coloured semi-matt background. Symbols, lettering and borders in semi- matt black or in Class I retro-reflective material, where the sign board is constructed from:
| C11.6.1.3 |  |  | Prepainetd Galvanised steel plate | 0.04
|  | (a) |  | Area 0 to 0.5m² | square metre (m²) | 15 | 1.26 | 0 | 0 | 0 | 650 | 9750 | 819 | 8931
|  | (b) |  | Area exceeding 0.5m² but not 2.0m² | square metre (m²) | 5 | 46.24 | 0 | 0 | 0 | 680 | 3400 | 31443.2 | -28043.2
|  | (c) |  | Area exceeding 2m² but not 10m² | square metre (m²) | 90 | 31.87 | 0 | 0 | 0 | 700 | 63000 | 22309 | 40691
|  | (d) |  | Area exceeding 10m² | square metre (m²) | 90 | 10.16 | 0 | 0 | 0 | 715 | 64350 | 7264.4 | 57085.6
| C11.6.1.8 |  |  | Regulatory signs, temporary |  |  | 0
|  | (b) |  | 900mm diameter (prepainted galvanised sheeting with class III retroreflective backgrounds and borders and semi matt symbols) | number (No.) | 6 | 0 | 0 | 0 | 0 | 650 | 3900 | 0 | 3900
| C11.6.1.9 |  |  | Warning Signs, permanent |  |  | 0
|  | (c) |  | 1200mm diameter (prepainted galvanised sheeting with class III retroreflective backgrounds and borders and semi matt symbols) | number (No.) | 2 | 24 | 0 | 0 | 0 | 1200 | 2400 | 28800 | -26400
| C11.6.1.11 |  |  | Supplementary plates to permanent regulatory or warning signs (prepainted galvanised sheeting with class III retroreflective backgrounds and borders and semi matt symbols) | square metre (m²) | 10 | 5.61 | 0 | 0 | 0 | 1200 | 12000 | 6732 | 5268
C11.6.2 |  |  |  | Extra over on item C11.6.1 for using: |  |  | 0
| C11.6.2.1 |  |  | Background of retro-reflective material: |  |  | 0
|  | (a) |  | Class I | square metre (m²) | 40 | 0 | 0 | 0 | 0 | 650 | 26000 | 0 | 26000
| C11.6.2.2 |  |  | Lettering, symbols, Nos, arrows, emblems and borders of retro-reflective material: |  |  | 0
|  | (b) |  | Class III | square metre (m²) | 40 | 0 | 0 | 0 | 0 | 650 | 26000 | 0 | 26000
C11.6.3 |  |  |  | Road sign supports (overhead road sign structures excluded) |  |  | 0
| C11.6.3.1 |  |  | Steel tubing (150Ø ) | ton (t) | 25 | 0 | 0 | 0 | 0 | 3500 | 87500 | 0 | 87500
| C11.6.3.2 |  |  | Timber (150Ø and CCA treated) | metre (m) | 60 | 236 | 0 | 0 | 0 | 150 | 9000 | 35400 | -26400
C11.6.5 |  |  |  | Excavation and backfilling for road sign supports (not applicable for kilometer posts) |  |  | 0
| C11.6.5.1 |  |  | Excavating soft material and backfilling | cubic metre (m³) | 40 | 40 | 0 | 0 | 0 | 125 | 5000 | 5000 | 0
| C11.6.5.2 |  |  | Extra over on item C11.6.5.1 for hard material excavation | cubic metre (m³) | 4 | 4 | 0 | 0 | 0 | 900 | 3600 | 3600 | 0
C11.6.10 |  |  |  | Disposing of road signs with surface area of: |  |  | 0
| C11.6.10.1 |  |  | Area 0 to 0.5m² | square metre (m²) | 15 | 1.26 | 0 | 0 | 0 | 60 | 900 | 75.6 | 824.4
| C11.6.10.2 |  |  | Area exceeding 0.5m² but not 2.0m² | square metre (m²) | 10 | 70.24 | 0 | 0 | 0 | 60 | 600 | 4214.4 | -3614.4
| C11.6.10.3 |  |  | Area exceeding 2.0m² but not 10.0m² | square metre (m²) | 100 | 31.87 | 0 | 0 | 0 | 60 | 6000 | 1912.2 | 4087.8
| C11.6.10.4 |  |  | Area exceeding 10m² | square metre (m²) | 90 | 10.16 | 0 | 0 | 0 | 60 | 5400 | 609.6 | 4790.4
TOTAL CARRIED FORWARD TO SUMMARY | [11 empty] | 328800 | 148179.4 | 180620.6 |  | 180620.6
C11.7 |  |  |  | ROAD MARKINGS AND ROAD STUDS
C11.7.2 |  |  |  | Retro-reflective road marking:
| C11.7.2.1 |  |  | White lines broken or unbroken (solvent based paint 100mm width) | kilometre (km) | 58 | 55.75 | 0 | 0 | 0 | 6500 | 377000 | 362375 | 14625 | [6 empty] | 3311 | 184588.25
| C11.7.2.2 |  |  | Yellow lines broken or unbroken (solvent based paint 100mm width) | kilometre (km) | 50 | 66.9 | 0 | 0 | 0 | 6500 | 325000 | 434850 | -109850 | [6 empty] | 3311 | 221505.9
| C11.7.2.4 |  |  | White and yellow lettering and symbols (solvent based) | square metre (m²) | 200 | 200 | 0 | 0 | 0 | 80 | 16000 | 16000 | 0 | [6 empty] | 260.15 | 52030
| C11.7.2.7 |  |  | Transverse lines, painted island and arrestor bed markings (any colour) (paint type indicated) | square metre (m²) | 1000 | 1632.7568 | 0 | 0 | 0 | 80 | 80000 | 130620.544 | -50620.544 | [6 empty] | 277.89 | 453726.7872
C11.7.3 |  |  |  | Thermoplastic road marking
| C11.7.3.1 |  |  | Thermoplastic road marking, broken or unbroken
|  | (a) |  | White lines broken or unbroken 100mm width | kilometre (km) | 53 | 55.75 | 0 | 0 | 0 | 5500 | 291500 | 306625 | -15125 | [6 empty] | 3784 | 210958
|  | (b) |  | Yellow lines broken or unbroken 100mm width | kilometre (km) | 45 | 66.9 | 0 | 0 | 0 | 5500 | 247500 | 367950 | -120450 | [6 empty] | 3784 | 253149.6
C11.7.5 |  |  |  | Variations in rate of application :
| C11.7.5.1 |  |  | White paint | litre (ℓ) |  | 0 |  |  |  | 21 |  | Rate only
| C11.7.5.2 |  |  | Yellow paint | litre (ℓ) |  | 0 |  |  |  | 21 |  | Rate only
| C11.7.5.4 |  |  | Retro-reflective beads | kilogram (kg) |  | 0 |  |  |  | 21 |  | Rate only
| C11.7.5.5 |  |  | Thermoplastic material, all colours | kilogram (kg) |  | 0 |  |  |  | 21 |  | Rate only
C11.7.7 |  |  |  | Road studs
| C11.7.7.1 |  |  | Permanent road studs compliant to SANS 1442 (100mm X 100mm x 20mm plastic stick on type with 43 bead glass reflectors - Bi-directional (any colour) | number (No.) | 9200 | 9291.67 | 0 | 0 | 0 | 460 | 4232000 | 4274168.2 | -42168.2 | [6 empty] | 84.62 | 786261.1154
| C11.7.7.3 |  |  | Temporary road studs compliant to SANS 1442 (100mm X 100mm x 20mm plastic stick on type with 43 bead glass reflectors - Bi-directional (any colour) | number (No.) | 12270 | 9291.67 | 0 | 0 | 0 | 200 | 2454000 | 1858334 | 595666 | [6 empty] | 36.66 | 340632.6222
C11.7.8 |  |  |  | Setting out and premarking the lines (excluding traffic island markings, lettering and symbols) | kilometre (km) | 130 | 132 | 0 | 0 | 0 | 65 | 8450 | 8580 | -130 | [6 empty] | 591.25 | 78045
C11.7.9 |  |  |  | Re-establishing the painting unit during the defects notification period and at other instances on instruction of the Engineer | number (No.) | 3 | 3 | 0 | 0 | 0 | 18000 | 54000 | 54000 | 0 |  |  | C1.2 | Pg 1 | 19376165.88 |  | 5912.5 | 17737.5
C11.7.11 |  |  |  | Removal of existing road studs | number (No.) | 9200 | 9200 | 0 | 0 | 0 | 30 | 276000 | 276000 | 0 |  |  | C1.3 | Pg 1 | 24229674.5 |  | 17.74 | 163208
[14 empty] | 0 |  |  | C1.4 | Pg 2 | 2871850
TOTAL CARRIED FORWARD TO SUMMARY | [11 empty] | 8361450 | 8089502.744 | 271947.256 |  | 271947.256 | C1.5 | Pg 3 | 7669396 |  |  | 2761842.7748
[17 empty] | C1.6 | Pg 3 | 3305250
C11.9 |  |  |  | FINISHING THE ROAD AND ROAD RESERVE AND TREATING OLD ROADS | [12 empty] | C3.1 | Pg 3 | 3460162.5
C11.9.1 |  |  |  | Finishing the road and road reserve: | [12 empty] | C3.3 | Pg 4 | 3657850
| C11.9.1.2 |  |  | Single carriageway road | kilometre (km) | 22.3 | 22.3 | 0 | 0 | 0 | 19000 | 423700 | 423700 | 0 |  |  | C4.3 | Pg 4 | 1100000 |  | 13277.9 | 296097.17
TOTAL CARRIED FORWARD TO PAGE 3 | [11 empty] | 423700 | 423700 | 0 |  | 0 | C8.5 | Pg 4 | 84940 |  |  | 296097.17
[17 empty] | C8.8 | Pg 4 | 8268600
C13.7 |  |  |  | JOINTS | [12 empty] | C8.9 | Pg 4 | 1292500
C13.7.5 |  |  |  | Supply and installation of Agrément South Africa certified proprietary expansion joints | [12 empty] | C9.1 | Pg 4 | 62069100
| C13.7.5.2 |  |  | Asphaltic plug type joints | [12 empty] | C11.4 | Pg 5 | 9066350
|  | (b) |  | 300mm x 50mm | metre (m) | 170 | 98.4 | 0 | 0 | 0 | 1700 | 289000 | 167280 | 121720 |  |  | C11.6 | Pg 5 | 328800 |  | 2293.5 | 225680.4
|  | (g) |  | Extra over for variation in joint depth of asphaltic joints | litre (ℓ) | 85 | 85 | 0 | 0 | 0 | 21 | 1785 | 1785 | 0 |  |  | C11.7 | Pg 5 | 8361450 |  | 88 | 7480
| C13.7.5.3 |  |  | Provision of Engineering Drawings af Proprietory joints and certification after instalation by an ECSA registered proffesional Engineer or technologist | lump sum | 1 | 1 | 0 | 0 | 0 | 100000 | 100000 | 100000 | 0 |  |  | C11.9 | Pg 5 | 423700
[17 empty] | C13.7 | Pg 5 | 123035
TOTAL CARRIED FORWARD TO SUMMARY | [11 empty] | 390785 | 269065 | 121720 |  | 121720 | C20.1 | Pg 6 | 585000 |  |  | 233160.4
[17 empty] | D1000 | Pg 6 | 18154356
C20.1 |  |  |  | TESTING MATERIALS AND JUDGEMENT OF WORKMANSHIP
C20.1.2 |  |  |  | Special tests requested by the Engineer
| C20.1.2.2 |  |  | Employer's contribution to other special tests
|  | (a) |  | Other tests required by the engineer | prime cost (PC) Sum | 1 | 0 | 0 | 0 | 0 | 1500000 | 1500000 | 0 | 1500000 | Likely no tests. Need to discuss Mods, compaction uner drains etc
|  |  | (i) | Handling costs and profit in respect of item C20.1.2.2(a) | percentage (%) | 1500000 | 0 | 0 | 0 | 0 | 10% | 150000 | 0 | 150000
PC20.1.5 |  |  |  | Financial contribution for an independent site laboratory (to be a negative rate) | month | 9 | 9 | 0 | 0 | 0 | -485000 | -4365000 | -4365000 | 0
PC20.1.6 |  |  |  | Payment of Independent site laboratory
| C20.1.6.1 |  |  | Direct payment by contractor | prime cost (PC) Sum | 1 | 0 | 0 | 0 | 0 | 3000000 | 3000000 | 0 | 3000000 | TBD- Late Completion
|  | (a) |  | Handling cost and profit in respect of item C20.1.6.1 | percentage (%) | 3000000 | 0 | 0 | 0 | 0 | 10% | 300000 | 0 | 300000 | TBD- Late Completion
TOTAL CARRIED FORWARD TO SUMMARY | [11 empty] | 585000 | -4365000 | 4950000 |  | 4950000
D1000 |  |  |  | TRAINING, COACHING, GUIDANCE, MENTORING AND ASSISTANCE
D10.01 |  |  |  | Target Group Participation
|  | (a) |  | Contract Participation Performance Bonus | prime cost (PC) sum | 1 | 1 | 0 | 0 | 0 | 1900000 | 1900000 | 1900000 | 0
D10.02 |  |  |  | Stakeholder and Community Liaison and Social Facilitation
|  | (a) |  | Cost of liaison, social facilitation and PLC support | prime cost (PC) sum | 1 | 0.4964 | 0 | 0 | 0 | 500000 | 500000 | 248200 | 251800
|  | (b) |  | Handling cost and profit in respect of sub-item D10.02(a) | percentage (%) | 500000 | 248200 | 0 | 0 | 0 | 10% | 50000 | 24820 | 25180
D10.03 |  |  |  | Tender Process for Targeted Enterprises
|  | (a) |  | Contractor’s charge for the management and execution of the Targeted Enterprise procurement process:
|  |  | (i) | Procurement process for the totality of all tenders concluded for the appointment of Targeted Enterprise subcontractors of CIDB 1 and 2 contractor grading | number (No.) | 6 | 14 | 0 | 0 | 0 | 10000 | 60000 | 140000 | -80000 | Latest CPG Plan
|  |  | (ii) | Procurement process for the totality of all tenders concluded for the appointment of Targeted Enterprise subcontractors of CIDB 3 and 4 contractor grading | number (No.) | 3 | 5 | 0 | 0 | 0 | 10000 | 30000 | 50000 | -20000 | Latest CPG Plan
|  |  | (iii) | Procurement process for the totality of all tenders concluded for the appointment of Targeted Enterprise subcontractors of CIDB 5 and higher contractor grading | number (No.) | 4 | 1 | 0 | 0 | 0 | 10000 | 40000 | 10000 | 30000 | Latest CPG Plan
|  |  | (iv) | Procurement process for the totality of all tenders concluded for the appointment of Targeted Enterprise suppliers | number (No.) | 13 | 3 | 0 | 0 | 0 | 10000 | 130000 | 30000 | 100000 | Latest CPG Plan
|  | (b) |  | Targeted Enterprise Procurement Coordinator | month | 9 | 9 | 0 | 0 | 0 | 25000 | 225000 | 225000 | 0
D10.04 |  |  |  | Responsibilities of the Contractor towards Targeted Enterprises
|  | (a) |  | Contractor’s establishment, management, management support, assistance, coaching, guidance, mentoring and supervision of Targeted Enterprises | month | 9 | 9 | 0 | 0 | 0 | 35000 | 315000 | 315000 | 0
|  | (b) |  | Targeted Enterprise Construction Manager | Person.Month | 9 | 9 | 0 | 0 | 0 | 95000 | 855000 | 855000 | 0
|  | (c) |  | Targeted Enterprise Site Supervisors | Person.Month | 36 | 18 | 0 | 0 | 0 | 20000 | 720000 | 360000 | 360000 | Assume 3 no will be provided for 6 months
D10.05 |  |  |  | Construction Works by Targeted Enterprises
|  | (a) |  | Payments associated with the construction works carried out by Targeted Enterprise subcontractors of CIDB 1 and 2 contractor grading designation appointed in terms of Section D | provisional sum | 1 | 0 | 0 | 0 | 0 | 2000000 | 2000000 | 0 | 2000000 | Value to be paid from main BOQ
|  | (b) |  | Handling costs and profit in respect of payment associated with sub-item D10.05(a) | percentage (%) | 2000000 | 0 | 0 | 0 | 0 | 10% | 200000 | 0 | 200000 | Value to be paid from main BOQ
|  | (c) |  | Fluctuation between the main contractor’s rates and that of the Targeted Enterprise subcontractors | lump sum | 1 | 1 | 0 | 0 | 0 | 200000 | 200000 | 200000 | 0 | Like low and will be utilised
|  | (d) |  | Preliminary and General Obligations of Targeted Enterprise sub-contractors appointed in terms of Section D | lump sum | 1 | 0.6 | 0 | 0 | 0 | 9456356 | 9456356 | 5673813.6 | 3782542.4 | Reducing this and moving to asphalt would not make a difference as the Contractor carries the shortfall anyway
D10.06 |  |  |  | Training, coaching, guidance, mentoring and assistance
|  | (a) |  | Training Costs
|  |  | (i) | Accredited NQF skills training | provisional sum | 1 | 1 | 0 | 0 | 0 | 300000 | 300000 | 300000 | 0 | Not yet confirmed
|  |  | (ii) | Accredited generic skills training | provisional sum | 1 | 1 | 0 | 0 | 0 | 300000 | 300000 | 300000 | 0 | Not yet confirmed
|  |  | (iii) | Community skills training | provisional sum | 1 | 1 | 0 | 0 | 0 | 100000 | 100000 | 100000 | 0 | Not yet confirmed
|  |  | (iv) | Handling cost and profit in respect of subitems D10.06(a)(i), (ii) and (iii) | percentage (%) | 400000 | 400000 | 0 | 0 | 0 | 10% | 40000 | 40000 | 0 | Not yet confirmed
|  | (b) |  | Student experiential training | prime cost (PC) Sum | 1 | 1.8 | 0 | 0 | 0 | 160000 | 160000 | 288000 | -128000 | 3 students for 12 months
|  |  | (i) | Student stipends | Person.Month | 18 | 36 | 0 | 0 | 0 | 3500 | 63000 | 126000 | -63000 | 4 students for 12 months
|  | (c) |  | Other costs during training | provisional sum | 1 | 1 | 0 | 0 | 0 | 500000 | 500000 | 500000 | 0 | This may likely not be done
|  | (d) |  | Training venue | lump sum | 1 | 1 | 0 | 0 | 0 | 10000 | 10000 | 10000 | 0 | Actual
TOTAL CARRIED FORWARD TO SUMMARY | [11 empty] | 18154356 | 11695833.6 | 6458522.4 |  | 6458522.4
[7 empty] | Checks |  |  |  |  | 174685910 | 174688149.0373 | -2239.0373
Note on I171: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: No rate for 1200 signs

## BoQ Summary
SUMMARY OF SCHEDULE OF QUANTITIES
SCHEDULE A : ROAD CONSTRUCTION
SECTION | DESCRIPTION | TENDER AMOUNT | ESTIMATE AMOUNT |  | Variance | TEN Civils
C1.2 | GENERAL REQUIREMENTS AND PROVISIONS | 19376146 | 896592.6 |  | 18479553.4
C1.3 | THE CONTRACTOR'S SITE ESTABLISHMENT AND GENERAL OBLIGATIONS | 24229674.5 | 18978234.5 |  | 5251440 | 4615878.5 | 4.328%
C1.4 | FACILITIES FOR THE ENGINEER | 2871850 | 2033976.7429 |  | 837873.2571
C1.5 | ACCOMMODATION OF TRAFFIC | 7659396 | 7440918 |  | 218478
C1.6 | CLEARING AND GRUBBING | 3305250 | 934370 |  | 2370880
C3.1 | DRAINS | 3460162.5 | 1980663 |  | 1479499.5
C3.3 | CONCRETE KERBING AND CHANNELING, ASPHALT BERMS, CHUTES, DOWNPIPES, AS WELL AS CONCRETE, STONE PITCHED AND GABION LININGS FOR OPEN DRAINS | 3657850 | 1509792.0083 |  | 2148057.9917
C4.3 | EXISTING ROAD MATERIALS | 1100000 | 0 |  | 1100000
C8.5 | STANDARD CRACK SEALING | 84940 | 0 |  | 84940
C8.8 | PATCHING AND EDGE BREAK REPAIR | 8268600 | 3608965.35 |  | 4659634.65 | 6251557.9942
C8.9 | REPAIR OF SURFACE DEFECTS | 1292500 | 1480600 |  | -188100 | 1036966.5
C9.1 | ASPHALT LAYERS | 62069100 | 106746019.25 |  | -44676919.25 | 96068323.7644 | 10677695.4856
C11.4 | ROAD RESTRAINT SYSTEMS | 9066350 | 12816736.8421 |  | -3750386.8421
C11.6 | ROAD SIGNS | 328800 | 148179.4 |  | 180620.6
C11.7 | ROAD MARKINGS AND ROAD STUDS | 8361450 | 8089502.744 |  | 271947.256 | 2761842.7748
C11.9 | FINISHING THE ROAD AND ROAD RESERVE AND TREATING OLD ROADS | 423700 | 423700 |  | 0 | 296097.17
C13.7 | JOINTS | 390785 | 269065 |  | 121720 | 233160.4
C20.1 | TESTING MATERIALS AND JUDGEMENT OF WORKMANSHIP | 585000 | -4365000 |  | 4950000
TOTAL SCHEDULE A : ROAD CONSTRUCTION |  | 156531554 | 162992315.4373 |  | 11569376.9373 | 111263827.1034 | 51728488.334
TOTAL ROADWORKS |  | 156531554 | 162992315.4373 | 0 | 11569376.9373 | 111263827.1034
SECTION
D1000 | TRAINING, COACHING, GUIDANCE, MENTORING AND ASSISTANCE | 18154356 | 11695833.6 | 6458522.4 | 11695833.6
TOTAL SCHEDULE D : STAKEHOLDER AND COMMUNITY LIAISON, AND TARGETED LABOUR AND TARGETED ENTERPRISES UTILISATION AND DEVELOPMENT |  | 18154356 | 11695833.6 | 6458522.4 | 11695833.6
GRAND TOTAL |  | 174685910 | 174688149.0373 | 6458522.4 | 23265210.5373
151420699.4627
CALCULATION OF TENDER SUM
TOTAL SCHEDULE A : ROAD CONSTRUCTION |  | 156531554 | 162992315.4373 |  |  | 111263827.1034
TOTAL SCHEDULE D : STAKEHOLDER AND COMMUNITY LIAISON, AND TARGETED LABOUR AND TARGETED ENTERPRISES UTILISATION AND DEVELOPMENT |  | 18154356 | 11695833.6
TOTAL WORK |  | 174685910 | 174688149.0373 |  |  | 111263827.1034
VAT 15% |  | 26202886.5 | 26203222.3556 |  |  | 16689574.0655
TENDER SUM CARRIED TO FORM OF TENDER |  | 200888796.5 | 200891371.3929 |  |  | 127953401.1689
-2574.8929

## Guardrails
ITEM |  |  | DESCRIPTION | UNIT | QTY | RATE | AMOUNT |  | GUARDRAILS (LHS)
C11.4 |  |  | ROAD RESTRAINT SYSTEMS
C11.4.1 |  |  | Erecting of guardrails at 3.81m spacing |  |  |  |  | REF No. | KM MARKER | KM START | DISTANCE TO START | KM END | TOTAL LENGTH (KM) | STRAIGHT LENGTH (KM) | APPROACH LENGTH (KM) | DEPARTING LENGTH (KM) | REMARKS
| C11.4.1.1 |  | Complete galvanised system compliant to SANS 1350: on timber posts |  |  |  |  | 1 | 55.4 | 55.37 | 0.03 | 55.7 | 0.33147 | 0.29337 | 0.01905 | 0.01905
|  | (a) | on timber posts | metre (m) | 8800 | 1000 | 8800000 | 2 | 56.2 | 56.33 | 0.13 | 56.343 | 0.01524 | 0.01524 | 0 | 0 | End Wings
| C11.4.1.2 |  | Terminal sections for 3.81m guardrails comprising of: |  |  |  |  | 3 | 56.34 | 56.42 | 0.08 | 56.596 | 0.17526 | 0.13716 | 0.01905 | 0.01905
|  | (a) | End Wings to SANS 1350 | number (No.) | 0 | 800 | 0 | 4 | 57.4 | 57.5 | 0.1 | 57.752 | 0.25146 | 0.21336 | 0.01905 | 0.01905
C11.4.6 |  |  | Reflective plates |  |  |  |  | 5 | 58.2 | 58.3 | 0.1 | 58.466 | 0.16764 | 0.12954 | 0.01905 | 0.01905
| C11.4.6.1 |  | Steel Plates | number (No.) | 1157.8947 | 15 | 17368.4211 | 6 | 59.4 | 59.421 | 0.021 | 59.585 | 0.16383 | 0.12573 | 0.01905 | 0.01905
C11.4.7 |  |  | Removing Existing Guardrails | metre (m) | 8800 | 380 | 3344000 | 7 | 60.6 | 60.59 | 0.01 | 60.722 | 0.13335 | 0.09525 | 0.01905 | 0.01905
C11.4.14 |  |  | Nailing of gang nail plates on top of timber guardrail posts | number (No.) | 2315.7895 | 55 | 127368.4211 | 8 | 61.8 | 61.9 | 0.1 | 62.125 | 0.22479 | 0.18669 | 0.01905 | 0.01905
C11.4.15 |  |  | Disposal of existing guardrails |  |  |  | 0 | 9 | 63.2 | 63.23 | 0.03 | 63.289 | 0.06096 | 0.02286 | 0.01905 | 0.01905
| C11.4.15.1 |  | Straight or curved long guardrails | metre (m) | 8800 | 60 | 528000 | 10 | 64.2 | 64.135 | 0.065 | 64.258 | 0.12192 | 0.08382 | 0.01905 | 0.01905
| C11.4.15.2 |  | End treatments with single guardrails | metre (m) | 0 | 80 | 0 | 11 | 65.6 | 65.67 | 0.07 | 65.862 | 0.1905 | 0.1524 | 0.01905 | 0.01905
[8 empty] | 12 | 66.4 | 66.49 | 0.09 | 66.653 | 0.16383 | 0.12573 | 0.01905 | 0.01905
[6 empty] | Total | 12816736.8421 | 13 | 67 | 66.952 | 0.048 | 67.084 | 0.13335 | 0.09525 | 0.01905 | 0.01905
[8 empty] | 14 | 67.4 | 67.42 | 0.02 | 67.626 | 0.20574 | 0.16764 | 0.01905 | 0.01905
[8 empty] | 15 | 68 | 68.08 | 0.08 | 68.31 | 0.2286 | 0.1905 | 0.01905 | 0.01905
[8 empty] | 16 | 68.6 | 68.65 | 0.05 | 68.848 | 0.19812 | 0.16002 | 0.01905 | 0.01905
[8 empty] | 17 | 69.2 | 69.19 | 0.01 | 69.369 | 0.17907 | 0.14097 | 0.01905 | 0.01905
[8 empty] | 18 | 69.6 | 69.65 | 0.05 | 69.735 | 0.08382 | 0.04572 | 0.01905 | 0.01905
[8 empty] | 19 | 70 | 70.11 | 0.11 | 70.203 | 0.09525 | 0.05715 | 0.01905 | 0.01905
[8 empty] | 20 | 71.2 | 71.28 | 0.08 | 71.535 | 0.25527 | 0.21717 | 0.01905 | 0.01905
[8 empty] | 21 | 72.2 | 72.32 | 0.12 | 72.588 | 0.2667 | 0.2286 | 0.01905 | 0.01905
[8 empty] | 22 | 73.4 | 73.51 | 0.11 | 73.658 | 0.14859 | 0.11049 | 0.01905 | 0.01905
|  |  |  | Guardrails (m) | 8800 |  |  | 23 | 74 | 74.04 | 0.04 | 74.0404 | 0.40767 | 0.36957 | 0.01905 | 0.01905
[10 empty] | TOTALS |  |  | 4.2024 | 3.3642 | 0.4191 | 0.4191
GUARDRAILS (LHS)
[8 empty] | REF No. | KM MARKER | KM START | KM END | KM END | TOTAL LENGTH (KM) | STRAIGHT LENGTH (KM) | APPROACH LENGTH (KM) | DEPARTING LENGTH (KM) | REMARKS
[8 empty] | 1 | 56.33 | 56.33 | 56.343 | 55.7 | 0.14478 | 0.14478 | 0 | 0 | End Wings
[8 empty] | 2 | 56.619 | 56.619 | 56.763 | 56.343 | 0.28575 | 0.24765 | 0.01905 | 0.01905
[8 empty] | 3 | 57.797 | 57.797 | 58.082 | 56.596 | 0.20193 | 0.16383 | 0.01905 | 0.01905
[8 empty] | 4 | 58.344 | 58.344 | 58.547 | 57.752 | 0.10287 | 0.06477 | 0.01905 | 0.01905
[8 empty] | 5 | 58.662 | 58.662 | 58.765 | 58.466 | 0.2286 | 0.1905 | 0.01905 | 0.01905
[8 empty] | 6 | 59.593 | 59.593 | 59.822 | 59.585 | 0.31242 | 0.27432 | 0.01905 | 0.01905
[8 empty] | 7 | 60.59 | 60.59 | 60.902 | 60.722 | 0.46101 | 0.42291 | 0.01905 | 0.01905
[8 empty] | 8 | 61.861 | 61.861 | 62.321 | 62.125 | 0.06096 | 0.02286 | 0.01905 | 0.01905
[8 empty] | 9 | 63.23 | 63.23 | 63.289 | 63.289 | 0.19431 | 0.15621 | 0.01905 | 0.01905
[8 empty] | 10 | 64.905 | 64.905 | 65.101 | 64.258 | 0.2286 | 0.1905 | 0.01905 | 0.01905
[8 empty] | 11 | 65.692 | 65.692 | 65.921 | 65.862 | 0.22098 | 0.18288 | 0.01905 | 0.01905
[8 empty] | 12 | 66.513 | 66.513 | 66.733 | 66.653 | 0.15621 | 0.11811 | 0.01905 | 0.01905
[8 empty] | 13 | 66.929 | 66.929 | 67.086 | 67.084 | 0.1143 | 0.0762 | 0.01905 | 0.01905
[8 empty] | 14 | 67.308 | 67.308 | 67.423 | 67.626 | 0.12954 | 0.09144 | 0.01905 | 0.01905
[8 empty] | 15 | 68.181 | 68.181 | 68.312 | 68.31 | 0.20955 | 0.17145 | 0.01905 | 0.01905
[8 empty] | 16 | 68.56 | 68.56 | 68.771 | 68.848 | 0.23241 | 0.19431 | 0.01905 | 0.01905
[8 empty] | 17 | 69.173 | 69.173 | 69.404 | 69.369 | 0.09525 | 0.05715 | 0.01905 | 0.01905
[8 empty] | 18 | 69.635 | 69.635 | 69.731 | 69.735 | 0.08382 | 0.04572 | 0.01905 | 0.01905
[8 empty] | 19 | 70.105 | 70.105 | 70.189 | 70.203 | 0.08763 | 0.04953 | 0.01905 | 0.01905
[8 empty] | 20 | 71.352 | 71.352 | 71.44 | 71.535 | 0.2667 | 0.2286 | 0.01905 | 0.01905
[8 empty] | 21 | 72.57 | 72.57 | 72.835 | 72.588 | 0.05715 | 0.01905 | 0.01905 | 0.01905
[8 empty] | 22 | 73.58 | 73.58 | 73.638 | 73.658 | 0.36576 | 0.32766 | 0.01905 | 0.01905
[8 empty] | 23 | 74.07 | 74.07 | 74.437 | 74.0704 | 0.36576 | 0.32766 | 0.01905 | 0.01905
[10 empty] | TOTALS |  |  | 4.6063 | 3.7681 | 0.4191 | 0.4191

## Road Marking
ITEM |  |  | DESCRIPTION | UNIT | QTY | RATE | AMOUNT
C11.7 |  |  | ROAD MARKINGS AND ROAD STUDS
C11.7.2 |  |  | Retro-reflective road marking: |  |  |  |  | KM (Start) | KM (End) | Position | Lane/Centerline | Type | Width (m) | Length (m) |  | Area (m^2) | Material | Condition | KM (Start) | KM (End) | Island ID | Height (m) | Width (m) | Area (m^2) | Material | Condition
| C11.7.2.1 |  | White lines broken or unbroken (solvent based paint 100mm width) | kilometre (km) | 55 | 6500 | 357500 | 44+000 | 74+300 | N2 | SBC | Yellow line | 0.1 | 22300 |  | 2230 | Thermoplastic | Worn Out | 43+900 | 44+027 | 1 | 79.6 | 6.01 | 239.198 | Thermoplastic | Worn Out
| C11.7.2.2 |  | Yellow lines broken or unbroken (solvent based paint 100mm width) | kilometre (km) | 44.6 | 6500 | 289900 | 44+000 | 74+300 | N2 | NBC | Yellow line | 0.1 | 22300 |  | 2230 | Thermoplastic | Worn Out | 46+700 | 46+892 | 2 | 192.03 | 3.35 | 321.6503 | Thermoplastic | Worn Out
| C11.7.2.4 |  | White and yellow lettering and symbols (solvent based) | square metre (m²) | 200 | 80 | 16000 | 44+000 | 44+022 | Extending from on ramp | NBC | Dotted White | 0.1 | 22 |  | 2.2 | Thermoplastic | Worn Out | 46+870 | 46+893 | 3 | 22.74 | 14.79 | 168.1623 | Thermoplastic | Worn Out
| C11.7.2.7 |  | Transverse lines, painted island and arrestor bed markings (any colour) (paint type indicated) | square metre (m²) | 1632.7568 | 80 | 130620.544 | 44+000 | 44+075 | N2 | SBC | Dotted White | 0.1 | 75 |  | 7.5 | Thermoplastic | Worn Out | 55+650 | 55+723 | 4 | 73.03 | 7.25 | 264.7337 | Thermoplastic | Worn Out
C11.7.3 |  |  | Thermoplastic road marking |  |  |  |  | 44+000 | 44+290 | N2 | Centerline | Solid Broken White Line | 0.1 | 290 |  | 29 | Thermoplastic | Worn Out | 64+800 | 64+873 | 5 | 73.03 | 8.25 | 301.2488 | Thermoplastic | Worn Out
| C11.7.3.1 |  | Thermoplastic road marking, broken or unbroken |  |  |  |  | 44+298 | 45+498 | N2 | Centerline | Broken White Line | 0.1 | 1200 |  | 120 | Thermoplastic | Worn Out | 65+600 | 65+673 | 6 | 73.03 | 9.25 | 337.7638 | Thermoplastic | Worn Out
|  | (a) | White lines broken or unbroken 100mm width | kilometre (km) | 55 | 5500 | 302500 | 45+498 | 45+506 | N2 | Centerline | Solid Broken White Line | 0.1 | 130 |  | 13 | Thermoplastic | Worn Out | [5 empty] | 1632.7568
|  | (b) | Yellow lines broken or unbroken 100mm width | kilometre (km) | 44.6 | 5500 | 245300 | 45+520 | 45+660 | N2 | NBC | Broken White Line | 0.1 | 140 |  | 14 | Thermoplastic | Worn Out
C11.7.5 |  |  | Variations in rate of application : |  |  |  | 0 | 45+715 | 45+739 | N2 | Centerline | Solid White Line | 0.1 | 24 |  | 2.4 | Thermoplastic | Worn Out
| C11.7.5.1 |  | White paint | litre (ℓ) |  | 21 | 0 | 45+741 | 45+839 | N2 | Centerline | Broken White Line | 0.1 | 98 |  | 9.8 | Thermoplastic | Worn Out
| C11.7.5.2 |  | Yellow paint | litre (ℓ) |  | 21 | 0 | 45+979 | 46+060 | N2 | Centerline | Dual Soild Broken White Line | 0.1 | 162 |  | 16.2 | Thermoplastic | Worn Out
| C11.7.5.4 |  | Retro-reflective beads | kilogram (kg) |  | 21 | 0 | 45+060 | 43+131 | N2 | Centerline | Solid Broken White Line | 0.1 | 71 |  | 7.1 | Thermoplastic | Worn Out
| C11.7.5.5 |  | Thermoplastic material, all colours | kilogram (kg) |  | 21 | 0 | 46+138 | 46+488 | N2 | Centerline | Broken White Line | 0.1 | 350 |  | 35 | Thermoplastic | Worn Out
C11.7.7 |  |  | Road studs |  |  |  |  | 46+495 | 46+845 | N2 | Centerline | Solid Broken White Line | 0.1 | 350 |  | 35 | Thermoplastic | Worn Out
| C11.7.7.1 |  | Permanent road studs compliant to SANS 1442 (100mm X 100mm x 20mm plastic stick on type with 43 bead glass reflectors - Bi-directional (any colour) | number (No.) | 9166.6667 | 460 | 4216666.6667 | 46+845 | 46+913 | N2 | Centerline | Dual Soild Broken White Line | 0.1 | 136 |  | 13.6 | Thermoplastic | Worn Out
| C11.7.7.3 |  | Temporary road studs compliant to SANS 1442 (100mm X 100mm x 20mm plastic stick on type with 43 bead glass reflectors - Bi-directional (any colour) | number (No.) | 9166.6667 | 200 | 1833333.3333 | 55+000 | 55+040 | N2 | Centerline | Broken White Line | 0.1 | 40 |  | 4 | Thermoplastic | Worn Out
C11.7.8 |  |  | Setting out and premarking the lines (excluding traffic island markings, lettering and symbols) | kilometre (km) | 132 | 65 | 8580 | 55+041 | 55+391 | N2 | Centerline | Solid Broken White Line | 0.1 | 350 |  | 35 | Thermoplastic | Worn Out
C11.7.9 |  |  | Re-establishing the painting unit during the defects notification period and at other instances on instruction of the Engineer | number (No.) | 3 | 18000 | 54000 | 55+350 | 55+510 | Extending from on ramp | NBC | Broken White Line | 0.1 | 160 |  | 16 | Thermoplastic | Worn Out
C11.7.11 |  |  | Removal of existing road studs | number (No.) | 9200 | 30 | 276000 | 55+516 | 55+736 | N2 | Centerline | Dual Soild Broken White Line | 0.1 | 440 |  | 44 | Thermoplastic | Worn Out
[8 empty] | 55+736 | 56+136 | N2 | Centerline | Solid Broken White Line | 0.1 | 400 |  | 40 | Thermoplastic | Worn Out
[6 empty] | Total | 7730400.544 | 56+142 | 58+842 | N2 | Centerline | Broken White Line | 0.1 | 2700 |  | 270 | Thermoplastic | Worn Out
[8 empty] | 58+846 | 59+082 | N2 | Centerline | Solid Broken White Line | 0.1 | 240 |  | 24 | Thermoplastic | Worn Out
[8 empty] | 59+090 | 59+142 | N2 | Centerline | Broken White Line | 0.1 | 52 |  | 5.2 | Thermoplastic | Worn Out
[8 empty] | 59+149 | 60+242 | N2 | Centerline | Solid Broken White Line | 0.1 | 1100 |  | 110 | Thermoplastic | Worn Out
[8 empty] | 59+349 | 59+849 | N2 | Centerline | Dual Soild Broken White Line | 0.1 | 1100 |  | 110 | Thermoplastic | Worn Out
[8 empty] | 60+248 | 62+148 | N2 | Centerline | Broken White Line | 0.1 | 1900 |  | 190 | Thermoplastic | Worn Out
[8 empty] | 62+155 | 62+805 | N2 | Centerline | Solid Broken White Line | 0.1 | 650 |  | 65 | Thermoplastic | Worn Out
[8 empty] | 62+455 | 62+519 | N2 | Centerline | Dual Soild Broken White Line | 0.1 | 128 |  | 12.8 | Thermoplastic | Worn Out
[8 empty] | 62+812 | 63+613 | N2 | Centerline | Broken White Line | 0.1 | 800 |  | 80 | Thermoplastic | Worn Out
[8 empty] | 63+620 | 64+470 | N2 | Centerline | Solid Broken White Line | 0.1 | 850 |  | 85 | Thermoplastic | Worn Out
[8 empty] | 64+020 | 64+120 | N2 | Centerline | Dual Soild Broken White Line | 0.1 | 200 |  | 20 | Thermoplastic | Worn Out
[8 empty] | 64+470 | 64+870 | N2 | Centerline | Broken White Line | 0.1 | 400 |  | 40 | Thermoplastic | Worn Out
[8 empty] | 64+877 | 66+270 | N2 | Centerline | Solid Broken White Line | 0.1 | 1400 |  | 140 | Thermoplastic | Worn Out
[8 empty] | 65+017 | 65+207 | Additional Lane | SBC | Broken White Line | 0.1 | 190 |  | 19 | Thermoplastic | Worn Out
[8 empty] | 65+061 | 65+107 | Additional Lane | NBC | Broken White Line | 0.1 | 46 |  | 4.6 | Thermoplastic | Worn Out
[8 empty] | 65+507 | 65+206 | N2 | Centerline | Dual Soild Broken White Line | 0.1 | 198 |  | 19.8 | Thermoplastic | Worn Out
[8 empty] | 65+386 | 65+516 | Extending from on ramp | NBC | Solid White Line | 0.1 | 130 |  | 13 | Thermoplastic | Worn Out
[8 empty] | 65+521 | 65+671 | Additional Lane | NBC | Broken White Line | 0.1 | 150 |  | 15 | Thermoplastic | Worn Out
[8 empty] | 65+749 | 65+810 | Additional Lane | SBC | Broken White Line | 0.1 | 61 |  | 6.1 | Thermoplastic | Worn Out
[8 empty] | 66+060 | 66+660 | N2 | Centerline | Broken White Line | 0.1 | 600 |  | 60 | Thermoplastic | Worn Out
[8 empty] | 66+667 | 66+360 | N2 | Centerline | Solid Broken White Line | 0.1 | 300 |  | 30 | Thermoplastic | Worn Out
[8 empty] | 66+360 | 67+010 | N2 | Centerline | Dual Soild Broken White Line | 0.1 | 1300 |  | 130 | Thermoplastic | Worn Out
[8 empty] | 67+010 | 67+200 | N2 | Centerline | Solid Broken White Line | 0.1 | 190 |  | 19 | Thermoplastic | Worn Out
[8 empty] | 67+200 | 67+253 | N2 | Centerline | Dual Soild Broken White Line | 0.1 | 106 |  | 10.6 | Thermoplastic | Worn Out
[8 empty] | 67+253 | 67+603 | N2 | Centerline | Solid Broken White Line | 0.1 | 350 |  | 35 | Thermoplastic | Worn Out
[8 empty] | 67+610 | 69+410 | N2 | Centerline | Broken White Line | 0.1 | 1800 |  | 180 | Thermoplastic | Worn Out
[8 empty] | 69+417 | 69+498 | N2 | Centerline | Solid Broken White Line | 0.1 | 88 |  | 8.8 | Thermoplastic | Worn Out
[8 empty] | 69+505 | 69+523 | N2 | Centerline | Broken White Line | 0.1 | 18 |  | 1.8 | Thermoplastic | Worn Out
[8 empty] | 69+530 | 69+780 | N2 | Centerline | Solid Broken White Line | 0.1 | 250 |  | 25 | Thermoplastic | Worn Out
[8 empty] | 69+780 | 69+900 | N2 | Centerline | Dual Soild Broken White Line | 0.1 | 420 |  | 42 | Thermoplastic | Worn Out
[8 empty] | 69+900 | 70+200 | N2 | Centerline | Broken White Line | 0.1 | 300 |  | 30 | Thermoplastic | Worn Out
[8 empty] | 70+207 | 71+100 | N2 | Centerline | Broken White Line | 0.1 | 900 |  | 90 | Thermoplastic | Worn Out
[8 empty] | 71+107 | 71+507 | N2 | Centerline | Solid Broken White Line | 0.1 | 400 |  | 40 | Thermoplastic | Worn Out
[8 empty] | 71+507 | 72+157 | N2 | Centerline | Dual Soild Broken White Line | 0.1 | 1300 |  | 130 | Thermoplastic | Worn Out
[8 empty] | 72+157 | 72+557 | N2 | Centerline | Solid Broken White Line | 0.1 | 400 |  | 40 | Thermoplastic | Worn Out
[8 empty] | 72+564 | 73+400 | N2 | Centerline | Broken White Line | 0.1 | 850 |  | 85 | Thermoplastic | Worn Out
[14 empty] | White | 26.305
[14 empty] | Yellow | 44.6

## Acc Traffic
ITEM |  |  |  | DESCRIPTION | UNIT | QTY | RATE | AMOUNT
C1.5 |  |  |  | ACCOMMODATION OF TRAFFIC
C1.5.1 |  |  |  | ACCOMMODATION OF PEDESTRIAN AND NON-MOTORISED TRAFFIC
| C1.5.1.1 |  |  | Accommodation of pedestrian and non-motorised traffic | month
C1.5.2 |  |  |  | Accommodation of vehicular traffic | month | 9 | 25000 | 225000
C1.5.3 |  |  |  | Liaison with traffic authorities | month | 9 | 5500 | 49500
PC1.5.7 |  |  |  | Temporary traffic control facilities
| C1.5.7.1 |  |  | Delineators including mounting bases and ballast:
|  | (a) |  | Single sided, reversible left or right
|  |  | (i) | Size 250 mm x 800mm | number (No) | 0 | 250 | 0
|  | (b) |  | Double sided, reversible left or right
|  |  | (i) | Size 250 mm x 800mm | number (No) | 1000 | 180 | 180000
| C1.5.7.2 |  |  | Traffic cones, minimum height 750mm | number (No) | 100 | 325 | 32500
| C1.5.7.3 |  |  | Flagmen | man-shift | 6510 | 540 | 3515400
| C1.5.7.4 |  |  | Traffic controllers | man-shift | 0 | 350 | 0
| C1.5.7.5 |  |  | Provision of illuminated traffic signs
|  | (a) |  | Sign mounted amber flashing lights (2 lights with the specified power supply) mounted on a backing board which is:
|  |  | (ii) | 1200mm wide x 200mm high | Number (No) | 6 | 6500 | 39000
|  | (b) |  | Flashing LED illuminated arrow board | Number (No) | 6 | 4500 | 27000
|  | (c) |  | Illuminated road sign – R & TR series (900 size) | Number (No) | 102 | 1634 | 166668
|  | (d) |  | Illuminated road sign – TW series (1200 size) | Number (No) | 0 | 1765.2 | 0 | Signs
|  | (g) |  | Illuminated road sign – TW series (1 200 mm size) | Number (No) | 0 | 580 | 0 | TR Ref. | No | 3 Closures
| C1.5.7.6 |  |  | Maintenance of illuminated traffic signs: |  |  |  | 0 | TR214 | 12 | 36
|  | (a) |  | Sign mounted flashing amber lights (a pair of two lights mounted on a separate backing board) | month | 9 | 500 | 4500 | TGS 107/108 | 10 | 30
|  | (b) |  | Flashing LED illuminated arrow board | month | 9 | 500 | 4500 | TIN 11.3 | 18 | 54
|  | (c) |  | Illuminated road sign – R & TR series (900 size) | month | 9 | 500 | 4500 | TR 201 -40 & 60 | 16 | 48
|  | (d) |  | Illuminated road sign – TW series (1200 size) | month | 9 | 500 | 4500 | TW 336 | 8 | 24
|  | (g) |  | Illuminated road sign – TG/TIN series | month | 9 | 500 | 4500 | TR104 | 6 | 18
| PC1.5.7.10 |  |  | Moveable traffic signs |  |  |  | 0 | TW411 | 3 | 9
|  | (a) |  | Regulatory signs. Temporary |  |  |  | 0
|  |  | (i) | R & TR series (900 diameter) | number | 102 | 150 | 15300 | Cones | 10
|  | (b) |  | Warning signs, temporary |  |  |  | 0
|  |  | (ii) | TW series (1 200 mm size) | number | 33 | 150 | 4950
|  | (c) |  | Portable STOP and GO-RY signs | number | 0 | 150 | 0
|  | (d) |  | Road signs, STW-, DTG-, TGS- AND TG-series (excluding delineators and barricades) | number | 30 | 150 | 4500
|  | (e) |  | Moveable barricade/road sign combination (8m wide chevron and road closed types) | number | 0 | 150 | 0
|  | (f) |  | TIN 11-3 (600m) | number | 0 | 150 | 0
|  | (g) |  | TIN 11-3 (400m) | number | 54 | 150 | 8100
|  | (h) |  | TIN 11-3 (200m) | number | 0 | 150 | 0
|  | (i) |  | TIN 11-4 (End/Thank you) | number | 0 | 150 | 0
C1.5.8 |  |  |  | Traffic safety officer | man-month | 15 | 90000 | 1350000
C1.5.9 |  |  |  | Traffic safety vehicle | month | 15 | 120000 | 1800000
C1.5.11 |  |  |  | Provision of safety equipment for visitors |  |  |  | 0
|  | C1.5.11.1 |  | Reflective safety vests for visitors | number (No) | 10 | 50 | 500
|  | C1.5.11.2 |  | Hard hats for visitors | No | 0 | 100000 | 0
C1.5.12 |  |  |  | Additional traffic accommodation facilities ordered by the Engineer: |  |  |  | 0
| C1.5.12.1 |  |  | Provision of additional traffic accommodation facilities | provisional sum | 0 | 100000 | 0
| C1.5.12.2 |  |  | Handling cost, profit and all other charges in respect of item C1.5.12.1 | percentage (%) | 0 | 0.1 | 0
[7 empty] | Total | 7440918
|  |  |  | Double sided |  |  | Flagmen
|  |  |  | No. of closures | 3 |  | No. of closures | 3
|  |  |  | Length (m) | 4000 |  | No. of flags per closure | 7
|  |  |  | Delineators spacing | 50 |  | No. of shifts | 2
|  |  |  | No. of Delienators per row | 80 |  | Days per month | 31
|  |  |  | No. of rows | 2 |  | No. Months | 5
[5 empty] | 160 |  |  | 6510
|  |  |  | Transitions | 40
|  |  |  | Total per closure | 200
|  |  |  | All closures | 600
|  |  |  | Markup | 120
|  |  |  | Total | 720
|  |  |  | Ordered by Contractor | 1000

## Road signs
ITEM |  |  | DESCRIPTION | UNIT | QTY | RATE | AMOUNT
C11.6 |  |  | ROAD SIGNS
C11.6.1 |  |  | Road signboards with painted or coloured semi-matt background. Symbols, lettering and borders in semi- matt black or in Class I retro-reflective material, where the sign board is constructed from:
| C11.6.1.3 |  | Prepainetd Galvanised steel plate | 0.04
|  | (a) | Area 0 to 0.5m² | square metre (m²) | 1.26 | 650 | 819
|  | (b) | Area exceeding 0.5m² but not 2.0m² | square metre (m²) | 46.24 | 680 | 31443.2
|  | (c) | Area exceeding 2m² but not 10m² | square metre (m²) | 31.87 | 700 | 22309
|  | (d) | Area exceeding 10m² | square metre (m²) | 10.16 | 715 | 7264.4
| C11.6.1.8 |  | Regulatory signs, temporary |  |  |  | 0
|  | (b) | 900mm diameter (prepainted galvanised sheeting with class III retroreflective backgrounds and borders and semi matt symbols) | number (No.) |  | 650 | 0
| C11.6.1.9 |  | Warning Signs, permanent |  |  |  | 0
|  | (c) | 1200mm diameter (prepainted galvanised sheeting with class III retroreflective backgrounds and borders and semi matt symbols) | number (No.) | 24 | 1200 | 28800
| C11.6.1.11 |  | Supplementary plates to permanent regulatory or warning signs (prepainted galvanised sheeting with class III retroreflective backgrounds and borders and semi matt symbols) | square metre (m²) | 5.61 | 1200 | 6732
C11.6.2 |  |  | Extra over on item C11.6.1 for using: |  |  |  | 0
| C11.6.2.1 |  | Background of retro-reflective material: |  |  |  | 0
|  | (a) | Class I | square metre (m²) |  | 650 | 0
| C11.6.2.2 |  | Lettering, symbols, Nos, arrows, emblems and borders of retro-reflective material: |  |  |  | 0
|  | (b) | Class III | square metre (m²) |  | 650 | 0
C11.6.3 |  |  | Road sign supports (overhead road sign structures excluded) |  |  |  | 0
| C11.6.3.1 |  | Steel tubing (150Ø ) | ton (t) |  | 3500 | 0
| C11.6.3.2 |  | Timber (150Ø and CCA treated) | metre (m) | 236 | 150 | 35400
C11.6.5 |  |  | Excavation and backfilling for road sign supports (not applicable for kilometer posts) |  |  |  | 0
| C11.6.5.1 |  | Excavating soft material and backfilling | cubic metre (m³) | 40 | 125 | 5000
| C11.6.5.2 |  | Extra over on item C11.6.5.1 for hard material excavation | cubic metre (m³) | 4 | 900 | 3600
C11.6.10 |  |  | Disposing of road signs with surface area of: |  |  |  | 0
| C11.6.10.1 |  | Area 0 to 0.5m² | square metre (m²) | 1.26 | 60 | 75.6
| C11.6.10.2 |  | Area exceeding 0.5m² but not 2.0m² | square metre (m²) | 70.24 | 60 | 4214.4
| C11.6.10.3 |  | Area exceeding 2.0m² but not 10.0m² | square metre (m²) | 31.87 | 60 | 1912.2
| C11.6.10.4 |  | Area exceeding 10m² | square metre (m²) | 10.16 | 60 | 609.6
[6 empty] | Total | 148179.4

## Overlay
ITEM |  |  | DESCRIPTION | UNIT | QTY | RATE | AMOUNT
C9.1 |  |  | ASPHALT LAYERS
C9.1.1 |  |  | Asphalt mix designs
| C9.1.1.2 |  | Sand skeletal mix:
|  | (a) | Continuously graded base or surfacing (PG58E-22,Level II mix design) | lump sum | 1 | 150000 | 150000
C9.1.2 |  |  | Construction of trial sections
| C9.1.2.1 |  | Asphalt layers (sand skeletal (continuosly graded) utilising an PG58E-22 binder with a maximum binder replacement of 15%, 50mm, paver placed) | square metre (m²) | 1920 | 212 | 407040
C9.1.3 |  |  | Application of bond coat
| C9.1.3.1 |  | Stable–grade 30% net bitumen emulsion as specified. Applied with a calibrated distributer | litre (ℓ) | 155765.5 | 13 | 2024951.5
| C9.3.1.3 |  | Applied by hand using brushes on all exposed transverse and longitudinal construction joints | litre (ℓ) | 200 | 21 | 4200
C9.1.5 |  |  | Asphalt surfacing
| C9.1.5.2 |  | Rehabilitation
|  | (e ) | Sand skeletal mix – continuously graded as defined (50mm, PG58E-22 utilising a maximum binder replacement of 15%, Level II mix design, paver placed) | ton (t) | 41441.375 | 1380 | 57189097.5
C9.1.9 |  |  | Application of Rolled in chips
| C9.1.9.1 |  | By means of a chip spreader | square metre (m²) | 0 | 15 | 0
C9.1.10 |  |  | Variation rates
| C9.1.10.1 |  | Bitumen (PG58E-22) | ton (t) |  | 3000 | 0
| C9.1.10.2 |  | Aggregate | ton (t) |  | 3000 | 0
| C9.1.10.3 |  | Active filler (lime unless stated in Contract Document) | ton (t) |  | 3500 | 0
C9.1.13 |  |  | Coring of asphalt layers
| C9.1.13.1 |  | 100mm diameter | number (No.) | 0 | 300 | 0
C9.1.14 |  |  | Surface regularity testing as described in Clause A9.1.8.4
| C9.1.14.1 |  | Establishment of equipment: Inertial laser Profilometer | number (No.) | 1 | 35000 | 35000
| C9.1.14.2 |  | Profiler Surveys utilising equipment as specified - Base layers and surfacing layers | lane kilometre (km) | 44.6 | 3500 | 156100
[6 empty] | Total | 59966389
|  |  |  | Bond coat |  |  | Asphalt surfacing |  | Based on m²
|  |  |  | Length | 22300 |  | Length | 22300 | 22300 | 50 | mm
|  |  |  | Width | 12.7 |  | Width | 12.7 | 12.7 | 45 | mm
|  |  |  | Area | 283210 |  | Area | 283210 | 283210 | 10%
|  |  |  | spray rate | 0.55 |  | Thickness | 0.05
|  |  |  | litre (ℓ) | 155765.5 |  | conv. Factor | 2.5
[8 empty] | 35401.25 |  |  |  | 14160.5 | m³ | 283210 | m² | Road
[7 empty] | 10% Allowence for thickness variations | 3540.125
[7 empty] | Allowence for ramps | 2500 | 16790 |  |  | 1000 | m³ | 16790 | m² | Ramps
[7 empty] | Tons | 41441.375 | 300000
[8 empty] | 102194430.75 |  |  |  | 15160.5 | m³ | 300000 | m²
[12 empty] | 303210 | m²

## Water-cutting
ITEM |  | DESCRIPTION | UNIT | QTY | RATE | AMOUNT
C8.9 |  | REPAIR OF SURFACE DEFECTS
C8.9.5 |  | Water Cutting
| C8.9.5.1 | Establishing of water cutting equipment on site | lump sum | 1 | 100000 | 100000
| C8.9.5.2 | Applying herbicides for sealing cracks | square metre (m²) | 34950 | 38 | 1328100
C8.9.6 |  | Trail sections for water cutting | square metre (m²) | 150 | 350 | 52500
[5 empty] | Total | 1480600
|  |  | Length | 23300
|  |  | Width | 1
|  |  | Lane / pulls | 1.5
34950

## Drains
ITEM |  |  | DESCRIPTION | UNIT | QTY | RATE | AMOUNT | QTY | RATE | AMOUNT
C3.1 |  |  | DRAINS
C3.1.1 |  |  | Excavation for open drain
|  | (a) | 0m - 1.5m | cubic metre (m³) | 990 | 105 | 103950 | 0 | 105 | 0 | No new unlined drains required
[7 empty] | 0 |  |  | 0
| C3.1.2.1 |  | Clearing, shaping and disposal of accumulated sediment in existing unlined open drains |  |  |  | 0 |  |  | 0
| C3.1.2.1 |  | Using conventional methods | cubic metre (m³) | 1930 | 105 | 202650 | 0 | 105 | 0 | May not be required
[7 empty] | 0 |  |  | 0
C3.1.3 |  |  | Excavation, clearing and disposal of accumulated sediment in existing lined drains and drainage systems |  |  |  | 0 |  |  | 0
| C3.1.3.1 |  | Using conventional methods (up to 1,5m): |  |  |  | 0 |  |  | 0
|  | (a) | Manholes and inlet and outlet structures | cubic metre (m³) | 200 | 190 | 38000 | 43.2 | 190 | 8208 | 1,2mX1,2mX1.0mX30no.
|  | (b) | Culvert barrels | cubic metre (m³) | 540 | 190 | 102600 | 540 | 190 | 102600 | Unknown at this stage
|  | (c) | (c)Concrete or other lined side drains | cubic metre (m³) | 1930 | 190 | 366700 | 1672.5 | 190 | 317775 | Assumed - 22300mX2no. X1.0mX0,075m*50%
[7 empty] | 0 |  |  | 0
C3.1.4 |  |  | Excavation and disposal of material for subsoil drainage systems: |  |  |  | 0 |  |  | 0
| C3.1.4.1 |  | Excavating in all materials situated within the following depth ranges below the surface: |  |  |  | 0 |  |  | 0
|  | (a) | 0m to 1.5m | cubic metre (m³) | 2460 | 190 | 467400 | 911.4 | 190 | 173166 | There is only sufficient concrete for 2170m of 1.0m wide drain
C3.1.5 |  |  | Impermeable backfilling to subsoil drainage system |  |  |  | 0 |  |  | 0
| C3.1.5.1 |  | Unstabilised natural gravel obtained from approved source on the site | cubic metre (m³) | 1720 | 75 | 129000 | 0 | 75 | 0
C3.1.7 |  |  | Natural permeable material in subsoil drainage systems |  |  |  | 0 |  |  | 0
| C3.1.7.2 |  | Crushed stone obtained from commercial sources | cubic metre (m³) | 500 | 650 | 325000 | 260.4 | 650 | 169260 | There is only sufficient concrete for 2170m of 1.0m wide drain
C3.1.8 |  |  | Natural permeable material in subsoil drainage systems (approved natural sand): |  |  |  | 0 |  |  | 0
| C3.1.8.2 |  | Natural sand from commercial sources | cubic metre (m³) | 250 | 650 | 162500 | 651 | 650 | 423150 | There is only sufficient concrete for 2170m of 1.0m wide drain
C3.1.9 |  |  | Pipes in subsoil drainage systems: |  |  |  | 0 |  |  | 0
| C3.1.9.1 |  | U-PVC pipes and fittings, normal duty, complete with couplings | metre (m) | 6132.5 | 65 | 398612.5 | 2170 | 65 | 141050 | There is only sufficient concrete for 2170m of 1.0m wide drain
C3.1.11 |  |  | Geotextiles (A1) |  |  |  | 0 |  |  | 0
| C3.1.11.1 |  | 0.15mm thick | square metre (m²) | 8590 | 35 | 300650 | 4057.9 | 35 | 142026.5 | There is only sufficient concrete for 2170m of 1.0m wide drain
C3.1.13 |  |  | Concrete outlet structures, manhole boxes, junction boxes and cleaning eyes for subsoil drainage systems |  |  |  | 0 |  |  | 0
| C3.1.13.4 |  | Cleaning eyes | number (No.) | 60 | 1450 | 87000 | 4 | 1450 | 5800 | Assumed 4 drains are going to be installed
C3.1.14 |  |  | Caps for subsoil drain pipes |  |  |  | 0 |  |  | 0
| C3.1.14.3 |  | Other (PVC) | number (No.) | 60 | 185 | 11100 | 8 | 185 | 1480 | Assumed 4 drains are going to be installed. Existing Rodding Eyes not found
C3.1.15 |  |  | Repairing or replacing existing drainage systems | provisional sum | 1 | 100000 | 100000 | 1 | 100000 | 100000
C3.1.22 |  |  | Test flushing of subsoil drain pipe system | number (No.) | 60 | 350 | 21000 | 4 | 350 | 1400 | Assumed 4 drains are going to be installed. Existing Rodding Eyes not found
C3.1/C1.7.2.2 |  |  | Hauling material to spoil and off-loading it at a designated spoil or stockpile area: |  |  |  | 0 |  |  | 0
|  | (a) | Cleared and grubbed material (organic matter and all other unsuitable or waste material) | cubic metre - kilometre (m³.km) | 92000 | 7 | 644000 | 56392.5 | 7 | 394747.5 | Above qty over a 25km haul distance
[6 empty] | Toat | 3460162.5 |  | Toat | 1980663

## Kerbs_conc drains
| ITEM |  | DESCRIPTION | UNIT | SCHEDULED QTY | RATE R | SCHEDULED AMOUNT
| C3.3 |  | CONCRETE KERBING AND CHANNELING, ASPHALT BERMS, CHUTES, DOWNPIPES, AS WELL AS CONCRETE, STONE PITCHED AND GABION LININGS FOR OPEN DRAINS
| C3.3.8 |  | Linings for open drains:
|  | C3.3.8.1 | Cast in situ concrete lining (Class 20/19 for open drains) as per drawing contained in Appendix 15 | square metre (m²) | 279.93 | 2100 | 587853
|  | C3.3.8.2 | ClassU2 surface finish to cast in situ concrete (Open Drains) | square metre (m²) | 2235.1 | 140 | 312914
| C3.3.9 |  | Formwork to cast in situ concrete lining for open drains (Class F2 surface finish):
|  | C3.3.9.1 | To sides with formwork on the internal face only | square metre (m²) | 542.5 | 430 | 233275
|  | C3.3.9.3 | To ends of slabs | square metre (m²) | 93.1292 | 430 | 40045.5417
| C3.3.10 |  | Sealed joints in concrete and stone pitched linings of open drains ((Polysulphide sealant) at 12m centres - Appendix 15) | metre (m) | 187.2883 | 65 | 12173.7417
| C3.3.12 |  | Reinforcement:
|  | C3.3.12.3 | Welded steel fabric (REF 193) | kilogram (kg) | 4313.743 | 75 | 323530.725
| TOTAL CARRIED FORWARD TO SUMMARY | [5 empty] | 1509792.0083
[6 empty] | Billed | 3657850
-2148057.9917
0 |  |  | Assumed length of Type E drain = | 2170 | m

## Patching
ITEM |  |  | DESCRIPTION | UNIT | QTY | RATE | AMOUNT
C8.8 |  |  | PATCHING AND EDGE BREAK REPAIR
C8.8.1 |  |  | Saw cutting pavement layers for patching
| C8.8.1.1 |  | Asphalt or bituminous surfacing to an average depth
|  | (a) | Not exceeding 50mm | metre (m) | 7000 | 56 | 392000
| C8.8.1.3 |  | Granular layers to an average depth
|  | (b) | Not exceeding 200mm | metre (m) | 7000 | 56 | 392000
C8.8.2 |  |  | Excavation in existing pavements for patching (non-milling)
| C8.8.2.3 |  | Crushed Stone layers
|  | (b) | Not exceeding 10 m² including for edge repairs wider than 250mm | cubic metre (m³) | 1090 | 340 | 370600
|  | (c) | Not exceeding 50 m² up to 100m² including for edge repairs wider than 250mm | cubic metre (m³) | 90 | 340 | 30600
|  | (d) | Exceeding 100m² | cubic metre (m³) | 1090 | 340 | 370600
| C8.8.2.4 |  | Asphalt layers
|  | (b) | Not exceeding 10 m² including for edge repairs wider than 250mm | cubic metre (m³) | 200 | 340 | 68000
|  | (c) | Not exceeding 50 m² up to 100m² including for edge repairs wider than 250mm | cubic metre (m³) | 20 | 340 | 6800
|  | (d) | Exceeding 100m² | cubic metre (m³) | 200 | 340 | 68000
C8.8.3 |  |  | Compacting the floor of excavations for patching (Compacted to 95% MDD) | square metre (m2) | 12000 | 45 | 540000
C8.8.4 |  |  | Backfilling of excavations for patching with:
| C8.8.4.3 |  | Asphalt for a patch with a surface area (sand skelatal (congtinuosly graded) utilising a PG58E-22 binder utilisinga maximum binder replacement of 15%, compacted to 97% -% design voids of MVD
|  | (b) | Not exceeding 10 m² including for edge repairs wider than 250mm | ton (t) | 2900 | 1000 | 2900000
|  | (c) | Not exceeding 50 m² up to 100m² including for edge repairs wider than 250mm | ton (t) | 230 | 1000 | 230000
|  | (d) | Exceeding 100m² | ton (t) | 2900 | 1000 | 2900000
[6 empty] | Toat | 8268600

## Clear and Grub
ITEM |  |  | DESCRIPTION | UNIT | QTY | RATE | AMOUNT
C1.6 |  |  | CLEARING AND GRUBBING
C1.6.1 |  |  | CLEARING
| C1.6.1.1 |  | Clearing with machines and some hard labour where necessary | hectare (ha) | 4.46 | 16500 | 73590
C1.6.2 |  |  | GRUBBING
| C1.6.2.1 |  | Grubbing with machines and some hard labour where necessary | hectare (ha) | 4.46 | 18000 | 80280
C1.6/C1.7.2 |  |  | HAULING
C1.6/C1.7.2.1 |  |  | Hauling material to spoil and off-loading it at a designated spoil or stockpile area:
|  | (a) | Cleared and grubbed material (organic matter and all other unsuitable or waste material) | cubic metre - kilometre (m³.km) | 111500 | 7 | 780500
[6 empty] | Toat | 934370
[5 empty] | Subcontractors | 6 | 155728.3333
|  |  |  | Length | 44600
|  |  |  | Width | 1
|  |  |  | Area | 44600
|  |  |  | Thickness | 0.1
|  |  |  | Volume | 4460
|  |  |  | Distance | 25 | Assumed Avarage
|  |  |  | Est. Haul | 111500
|  |  |  | Clearing in ha | 4.46